## PRESIDENT’S MANAGEMENT AGENDA

## ACTION PLANS FOR THE

## NATIONAL AERONAUTICS AND SPACE ADMINISTRATION

##### May 9, 2002

## Initials of NASA					Initials of OMB

## Representative: _________			Representative: _________

## TABLE OF CONTENTS

HUMAN CAPITAL	3

COMPETITIVE SOURCING	12

FINANCIAL MANAGEMENT	14

EXPANDING ELECTRONIC GOVERNMENT	16

BUDGET/PERFORMANCE INTEGRATION	19

PMA SCORECARD	21

# HUMAN CAPITAL

## CURRENT STATUS

OMB reports NASA's status as "red" for human capital.  NASA is in the process of developing an agency-wide human capital plan, has proposed new authorities to improve management of its human capital, and has committed to improving its workforce tracking.  However, NASA has yet to approve an agency-wide human capital plan, fully utilize its existing human capital management authorities, or implement an improved workforce tracking system.  Also, NASA needs to complete and submit to OMB a Transformation Workforce Restructuring Plan based on the Strategic Resources Review.  This will be critical, in conjunction with the Strategic Human Capital Plan, to ensuring that no skill gaps/deficiencies exist in mission critical occupations.

### NASA PLANS TO ACHIEVE YELLOW STATUS

Develop and Approve Agency Strategic Human Capital Plan

NASA will develop and approve an agency-level human capital plan and associated implementation plans.  NASA will submit its first full, Strategic Human Capital Plan to OPM and OMB no later than June 30, 2002.  At a minimum, this plan will address three key areas.

1)	Strategic Management of Critical Workforce Needs

NASA’s critical workforce competencies are not permanent or static, but are a portfolio of skills that changes over time as NASA’s needs change, with new competencies coming in and competencies no longer needed transitioning out.  To greatly improve the agility and flexibility of NASA's workforce, NASA's human capital plan will:

- Define the critical workforce competencies NASA needs to execute its approved programs over the next ten years – including permanent and non-permanent civil servants, and contracted workforce in industry and academia.

- Develop an agency-wide capability to track, project, and analyze critical workforce competencies that enables strategic management

- Identify imbalances in current and projected workforce of today, relative to what is needed for the future (oversupply/undersupply of key skills)

- Identify those workforce competencies that can or could be supplied through academia, industry or other organizations and those competencies that can only be met through a civil servant workforce.

- Identify the limited number of truly critical civil servant personnel needed for those competencies that NASA must retain in-house as well as those needed to oversee competencies supplied through academia, industry or other organizations.

- Identify and plan out the reforms needed to enable the competitive sourcing of those competencies that can or could be supplied through academia, industry or other organizations, including a schedule for each reform and an estimated range of the number of civil servant positions that could be affected each year (to be outlined in the NASA Competitive Sourcing Plan).

- Develop a lifecycle model for NASA’s workforce competencies to aid in their strategic management that includes three distinct phases: 1) identifying the need for then establishing new competencies; 2) assessing and maintaining the health of mature competencies; and 3) determining whether NASA no longer needs to provide a competency (either with in-house personnel or at all), and the process for transitioning NASA away from that competency.

2)	Creating and Expanding Organizational Agility

NASA must improve its agility as an organization, to adapt to the changing needs of the future.  This can be done with more institutional flexibility, more flexibility in the ability to shape the workforce, and more flexibility within the workforce itself at the individual employee level.

Management Authorities and Flexibility -- To improve the recruitment, retention, competency and flexibility of NASA's civil servant workforce, NASA's human capital plan will:

- Identify new authorities necessary to implement the reforms contained in NASA's Competitive Sourcing Plan.  These authorities could include (but proposals are not limited to):  benefits portability, extended buyout authority, retraining expenses for involuntarily separated employees, and waiver of reduction of annuity when reemploying civil servants (a menu of options will be attached to the Strategic Human Capital Plan).

- Identify new authorities that could improve the recruitment, retention, competency and flexibility of NASA's civil servant workforce.  These authorities could include: excepted service and distinguished scholar hiring authorities, scholarship for service, expanded use of term appointments and IPAs, simplified candidate evaluation, pay broad-banding, critical pay authority, and industry and academic exchange programs (a menu of options will be attached to the Strategic Human Capital Plan).

Civil Service Mix – Permanent and Non-Permanent -- To improve agility of the workforce, NASA’s plan will:

- Develop a strategy – tied to information from NASA capabilities in strategic management of human capital – that will enable the identification of the appropriate mix, over time, between permanent and non-permanent civil servants.

- Ensure that mechanisms and incentives are available for achieving the appropriate mix of non-permanent civil servants and IPAs (e.g. terms, temps, NEX, IPAs, etc.).

Employee Agility -- To improve agility of the individual employee, NASA’s human capital plan will:

- Include a plan that ensures that the norm is for employees to broaden their experience and skill base, as part of career advancement at NASA.

- Incorporate training and education activities to help make employees more agile.

## 3)	Assuring Future Leadership, Management and Technical Expertise

Recruitment and Retention

- Define strategies for improving ability to recruit and retain

Training and Education

- Define training and education priorities that assure NASA’s future needs can be met

Mentoring and Succession Planning -- To improve and ensure successful management of NASA's programs, NASA's plan will:

- Provide methods for identifying NASA civil servant program/project leaders and experts that are most critical to NASA executing its approved programs.

- Establish mentoring and knowledge sharing approaches and programs – driven by strategic needs -- that enable current leaders to transfer their expertise to future project leaders.

- Identify and use lessons learned from successes and failures to mentor and transfer critical knowledge and skills to future project leaders who need this development and knowledge.

Begin Implementation of Human Capital Plan:  To begin implementation of its Plan, NASA will complete the following actions.

1)	Strategic Management of Critical Workforce Needs

- Provide a progress report and quarterly accomplishments relative to OPM’s Human Capital scorecard by June 30, 2002

- Complete Competency pilot at KSC by June 30, 2002

- Develop an Agencywide competency dictionary by July 30, 2002

- NASA has developed a phased approach to establishing and Agencywide workforce planning capability.  The first phase will involve updating and integrating the existing SRR workforce competency database by September 30, 2002.

- Identify critical competencies across the agency, those at risk, and potential skill mix adjustments between Centers by November 30, 2002.

- As a first step to assuring that employee rewards, recognition, and performance are linked to Agency key goals, the Agency will assess the current state of linkage using the OPM survey (December 2002).

2)	Creating and Expanding Organizational Agility

- NASA will develop HR tools and strategies that support major Agency transformation implementation plans—including competitive sourcing goals--and, as necessary, will offer legislative proposals to facilitate reforms (ongoing).

- By December 31, 2002 complete a study to evaluate the need for expanded mobility and rotational assignments to expand knowledge and experience of the workforce.

- By October 1, 2002 provide Enterprises/Centers mechanisms and incentives for hiring non-permanent employees.

- To support increasing the utilization of HR flexibilities to recruit, hire and retain a highly productive workforce, NASA Headquarters will delegate NEX authority to Centers (June 2002) and will identify critical positions where incentives are required (September 2002).

- NASA will roll out an automated classification system within the Integrated Financial Management Program (IFMP) (September 2002).

- The Agency will establish a NASA Education program linkage system that tracks students in NASA Education programs in order to link students in these programs to NASA hiring efforts for future workforce needs (September 2002).

## Assuring Future Leadership, Management and Technical Expertise

- By October 2002 develop a project leadership knowledge sharing and mentoring plan including strategic areas of priority, identification of critical leaders and experts who can share knowledge and mentor future project leaders, and begin pilot activities.

- By June 3, 2002 identify positions requiring critical position pay authority.

- Implement an enhanced agency-wide strategy to recruit and retain in critical competencies.

- Establish by November 30, 2002, key strategic skill area targets to shape recruitment of college hires for the summer of 2003 (feeding pipeline through middle of decade).

## NASA PLANS TO ACHIEVE GREEN STATUS

The OMB Core Criteria for Achieving Success are to achieve all of the following:

- Agency human capital strategy is aligned with mission, goals, and organizational objectives: 1) integrated into Budget and Strategic Plans; 2) consistent with OPM’s human capital balanced scorecard (issued by December 1, 2001); and 3) complies with standards for internal accountability systems to ensure effective merit-based HRM.

- Agency has a citizen-centered organizational structure that is delayered and oriented toward performing the mission assigned to it.

- Agency 1) sustains high-performing workforce that is continually improving in productivity; 2) strategically uses existing personnel flexibilities, tools, and technology; and 3) implements effective succession plans.

- No skill gaps/deficiencies exist in mission critical occupations.

- Agency differentiates between high and low performers through appropriate incentive and rewards.

- Changes in agency workforce skill mix and organizational structure reflect increased emphasis on e-government and competitive sourcing.

## Fully Implement Human Capital Plan

## To ensure full implementation of its Human Capital Plan and meet all criteria for achieving green status, NASA will undertake the following actions:

1)	Strategic Management of Critical Workforce Needs

- Complete rollout of KSC competency model Agencywide and resolve gaps and surplus competencies in mission critical occupations by September 30, 2003.

2)	Creating and Expanding Organizational Agility

- NASA will continue to incorporate human resources tools and strategies in major Agency transformation implementation plans, including legislative proposals, where necessary, to facilitate reforms (ongoing)

- By October 2003 evaluate results of mobility/rotation study, and pilot/implement actions to expand development activities as indicated by study results

- Identify strategically-derived goals for permanent/non-permanent mix, and implement a plan for achieving those goals.

- NASA will verify or – where FY 2002 assessment results indicate its absence – establish a linkage between employee rewards, recognition, and performance and Agency key goals (May 2003).

- NASA Headquarters will verify that delegation of NEX authority to the Centers has resulted in increased use of this flexibility (June 2003).

- NASA Headquarters will survey Agency managers to assess satisfaction with the automated hiring system module of the IFMP (September 2003).

## 3)	Assuring Future Leadership, Management and Technical Expertise

- Implement by October 1, 2003 new positions subject to critical position pay authority

- By October 2003 implement agencywide program and products – driven by strategic needs -- related to mentoring and transferring knowledge from critical project leader experts to mentor future project leaders.

- Implement by October 1, 2003 a training and education program that is aligned with strategic priorities based upon training needs

- NASA will incorporate the Strategic Human Capital Plan into the Agency’s strategic and performance planning processes (September 2003).

BACKGROUND

- NASA reduced its overall civil service workforce by 26 percent between FY 1993 and FY 2000 and reduced the Headquarters staff by 50 percent.  Organizational restructuring and reductions resulted in a 52 percent reduction in supervisory positions and a 15 percent reduction in SES.  On an Agencywide basis, the supervisor to employee ratio went from 1:6 to 1:10.

- Less than 13 percent of Agency authorized funding is spent on civil service salaries and benefits.  NASA accomplishes its work through the combined efforts of civil servants, contractors, and individuals from the academic world who contribute through post-doctoral fellowships, grants programs, Intergovernmental Personnel Assignments, and other partnerships.

- NASA has transferred major and critically important functions, such as the transfer of space launch and operations to an industry partnership and a consolidated contract with an industry team to handle space communications.  NASA established a contracting vehicle that outsources ownership and management of desktop computers, local servers, and other communications assets and services.

- Annual guidance for preparation of SES performance plans reflects ongoing requirement that all such plans be aligned with the NASA Strategic Plan.

- Three NASA Centers have been involved in the pilot of an automated tool to link NASA Strategic Plan goals and objectives to the individual’s performance plan.

- NASA has established partnerships with academia to provide fellowships in leadership and project management development, including partnership with the Massachusetts Institute of Technology in Project Management and with the University of Virginia’s Darden Business School to develop a Business Education Program.

- The Agency leadership model has been updated.  It specifies the latest cutting edge skills and behaviors required for effective leadership, and is linked to NASA’s Strategic Plan.

- NASA is addressing the critical “pipeline” issue to ensure a future pool of talent in science, engineering, math, and technology disciplines.  An Agency-wide Undergraduate Student Research Program pilot phase was initiated in FY 2001 with 107 students (55 male and 52 female students with 41 percent minority participation from 29 states and Puerto Rico, and represent 70 institutions).

- To enhance capability and reduce time away from work, NASA created and implemented additional on-line capabilities.  In FY 2001, the Agency increased training opportunities in technology-based learning by 127 percent from the FY 1999 baseline and increased employee use of technology-based learning opportunities by 122 percent.

NASA’S ACTIONS SINCE 9/30/01

- NASA began a Strategic Resources Review (SRR) in FY 2001 based on NASA’s future vision and mission to ensure that resources are prioritized and directed at the most critical Agency requirements and to focus on the Agency’s fundamental roles and missions.  There are many activities/actions being studied/explored under the SRR, with three major ones being actively explored.  They are Shuttle competitive sourcing, International Space Station (ISS) non-government organization (NGO), and Consolidated Business Services.

- NASA has developed a “menu” of legislative proposals for civil service reforms that may be needed to accomplish SRR transformational activities and to ensure NASA can recruit and retain top science, engineering, and management talent.

- NASA developed a human capital functional leadership plan to support the Agency Strategic Plan.  This plan is being superseded by a comprehensive Agency Strategic Human Capital Plan that conforms to the OMB and OPM scorecard criteria.  A team of senior NASA managers is currently developing a draft plan, to include goals, strategies, tactical plans, and success measures.

- NASA utilizes recruitment bonuses and retention allowances – a trend the Agency expects to continue because of an increasingly competitive job market and high cost of living in some areas.

- The Agency is re-establishing its recruitment networks and rebuilding once extensive Co-operative Education Program.  It continues to utilize the Presidential Management Intern Program and student employment programs as sources for entry-level hires.

- NASA is one of the first Federal agencies to hire individuals under new Federal Career Intern Program – a useful tool for hiring recent graduates in engineering and science.

- NASA has implemented a paperless hiring and competitive promotion system – greatly improving the speed of filling vacancies and improving the job-seeking experience for the public.  It has been nominated for Agency and Government-wide awards.

- The Agency established a National Recruitment Initiative to develop Agency-wide recruitment strategies to attract and hire a highly technical S&E workforce focusing on the candidate instead of the hiring process; leveraging partnerships and alliances with universities; and coordinating Agency-wide recruitment opportunities and outcomes.  The report was issued in March 2002, with tools to facilitate achieving an agile, flexible hiring model identified.  Three such tools are currently in the development stage.

- NASA was the first agency to implement the new Federal-wide program to repay student loans to attract or retain employees in critical positions.

- A variety of awards and performance recognition programs are in place.  The Agency is currently conducting a study on how recognition programs foster behaviors that lead to mission success.  Internal and external benchmarking is being used to identify critical factors for developing, using, communicating, and assessing recognition practices.

- The Agency continues to emphasize quality of work-life initiatives such as alternative work schedules, family-friendly leave programs, and employee assistance programs.

- NASA funds a minimum investment in learning of more than 3 percent of salary and plans continued investment at or above this percentage.

- NASA has enhanced the system architecture of the Site for Online Learning Resources (SOLAR) to support 50,000 learners.

- To improve project team competencies, emphasis has been placed on “just in time” training opportunities for project leaders and team members.

- Learning through simulations, as well as coaching and mentoring opportunities, are being pursued.

- The NASA Integrated Action Team (NIAT) identified actions to provide systems solutions to improve NASA’s ability to effectively execute its mission, ensuring application of best practices across spectrum of Agency programs and projects.  These actions are now underway.

- The Agency redesigned its Fellowship Program, which now requires Center management to document a reentry strategy to ensure learning acquired is applied to Agency-mission needs.  It includes a process to track related mission impacts resulting from the investment.

- Programs have been added to provide knowledge sharing forums and deliver targeted development workshops geared at assisting intact project teams in performing quality project management, incorporating lessons learned on other projects.

- NASA has long-term developmental processes in place that provide a critical tool for succession planning, including the Senior Executive Service Candidate Development Program and the Professional Development Program.  With a goal toward ensuring a strong, diverse candidate pool of potential future leaders, increased emphasis is being placed on assuring the right people are nominated for such programs.

- The Agency is developing program linkages/data system to link students supported by NASA Education Programs to Agency human capital requirements.

# COMPETITIVE SOURCING

#### CURRENT STATUS

OMB reports NASA’s status as “red” for competitive sourcing.  NASA has not completed public-private or direct conversion competition on 15 percent of the FTEs listed on the approved FAIR act inventories of commercial activities.    NASA is in the process of developing a plan for achieving competitive sourcing goals, and has agreed to undertake some key competitive sourcing reforms.  However, NASA has yet to complete its strategic resources review that may identify competitive sourcing opportunities, or lay out a concrete plan for meeting the government-wide 50 percent competitive sourcing goal.  NASA’s FAIR Act inventory may not reflect some of the FTEs that would be subject to planned competitive sourcing activities, therefore it is critical to get an updated FAIR Act inventory that accurately reflects commercial activities as soon as possible.

NASA PLANS TO ACHIEVE YELLOW STATUS

Develop a Competitive Sourcing Plan to transform the 40-year old national lab organizational model NASA uses to execute its programs and greatly improve the agility and flexibility of NASA’s workforce, NASA’s plan will:

- Clearly articulate the reasons for pursuing competitive sourcing and make the case why competitive sourcing is in the best long-term interest of NASA.

- Revise NASA’s FAIR Act Inventory to be consistent with the workforce competencies and classifications provided in the Human Capital Plan (i.e., all positions not classified as inherently governmental will be classified as commercial on the Inventory) by June 30, 2002.

- By June 30, 2002, provide an interim competitive sourcing plan that lays out NASA’s specific competitive sourcing activities with the exception of Space Shuttle competitive sourcing and a non-government organization for managing Space Station research.  This plan should provide an estimate of the specific FTE associated with and schedule for each activity.

  - At a minimum, the interim plan for these reforms should include: a University Affiliated Research Center (UARC) at Ames Research Center, competitive sourcing for technicians at NASA’s research centers, and, potentially, one consolidation effort with another government agency (e.g., DOD).

  - Reforms can include (but are not limited to): traditional OMB Circular A-76 competitions, conversions excepted from A-76 competition, consolidation with DOD or other federal agencies, and rehiring after attrition into new or existing contractor or partner organizations such as federally funded research and development centers (FFRDCs) or university affiliated research centers (UARCs).

- By September, 2002, provide a complete, integrated, agency-wide competitive sourcing plan that includes Space Shuttle competitive sourcing and a non-government organization (NGO) for Space Station in addition to the reforms provided in the interim plan.  This plan should, at a minimum, meet the long-term, government-wide 50-percent competitive sourcing goal and provide an estimate of the specific FTE associated with and schedule for each activity.

## Begin Implementation of Competitive Sourcing Plan

To begin implementation of its plan, NASA will move beyond planning to implementation of key activities including Shuttle competitive sourcing and Station NGO.   The plan should identify any necessary and appropriate exceptions to full competition per OMB Circular A-76.

### Begin Extending Competitive Sourcing Reform to Contracted Activities

To begin ensuring that both civil servant and contracted activities are subject to regular, recurring review and competition, NASA will initiate the following actions.

- Create a consolidated list of all Federally Funded Research and Development Centers (FFRDCs), University Affiliated Research Centers (UARCs), Commercial Centers for the Development of Space (CCDSs), University Research, Engineering and Technology Institutes (URETIs), and similar contracts and partnerships providing reimbursable support services by October 1, 2002.

- Put in place plans for reviews and recompetition of these contracts and partnerships by September 30, 2003.  At a minimum, plans will include mid-term review dates for any options to extend and a hard termination date of no greater than ten years with provisions for granting exceptions as appropriate.

NASA PLANS TO ACHIEVE GREEN STATUS

## Fully Implement Competitive Sourcing Plan

To ensure full implementation of its plan, NASA will take the following actions:

- Achieve Phase I of NASA’s competitive sourcing plan as approved by OMB (to be submitted on June 30, 2002) by September 30, 2003.

- Be on schedule for achieving Phase II of NASA’s approved competitive sourcing plan by September 30, 2003.

Final target commitments for Phase I and Phase II (e.g., 15% and 50%) will be based on the 2000 FAIR Act Inventory baseline and analysis to be completed by June 30, 2002.

### Fully Extend Competitive Sourcing Reform to Contracted Activities

To ensure that both civil servant and contracted activities are subject to regular review and competition, NASA will complete or have underway reviews and recompetitions for all contracts and partnerships that have reached their mid-term review date or their mandatory re-compete date.

# FINANCIAL MANAGEMENT

CURRENT STATUS

OMB reports NASA’s current status as “red” for financial management.  NASA had received a “clean” audit opinion for seven consecutive years and the auditors concluded that NASA had no material financial management weaknesses.  PricewaterhouseCoopers (PWC), an independent public accounting firm, audited NASA’s FY 2001 financial statements, and concluded that it could not express an opinion on the financial statements because NASA did not provide sufficient evidence, on a timely basis, to support certain amounts on the financial statements.  PWC also state that it identified a material weakness resulting from NASA’s lack of adequate controls to reasonably assure that property, plant, and equipment and materials are presented fairly in financial statements.

NASA is implementing a new, Integrated Financial Management (IFM) system.  However, the most critical component, the Core Financial module has not been fully implemented at the nine NASA field Centers and Headquarters.

NASA PLANS TO ACHIEVE YELLOW STATUS

NASA’s overall strategy to fully achieve the objectives of the financial management initiative is to (1) successfully implement its new IFM system and (2) resolve its material weakness and regain a “clean” audit opinion on its financial statements.

Implement IFM System

Due to the use of individual, non-integrated systems at Headquarters and field Centers to meet statutory and regulatory reporting requirements, NASA reports its financial systems as a significant area of management concern in its annual report pursuant to the requirements of the Federal Managers’ Financial Integrity Act.  The IFM program consists of a series of projects such as core finance, including budget execution; travel, and budget formulation.  While all components of the IFM Program are important, the successful completion of the Core Financial project is particularly critical to achieving the objectives of the improved financial management initiative and to implementation of full cost budgeting and management.  To continue progress towards full implementation of NASA’s IFM, NASA will achieve the following IFM implementation milestone:

- Successfully implement the IFMP Core Financial module at five field Centers and Headquarters (February 1, 2003)

Obtain “Clean” Opinion on FY 2002 Financial Statements

A team consisting of CFO Office staff, Center finance staff, and technical staff to address Station and Shuttle matters is addressing each of the problems identified by PWC in its FY 2001 financial statement audit.  To achieve a “clean” opinion on its FY 2002 financial statements, NASA will meet the following milestones:

- Resolve all outstanding issues resulting from the audit of NASA’s FY 2001 financial statements (July 31, 2002);

- Close FY 2002 financial records  (November 15, 2002);

- Obtain “clean” audit opinion on FY 2002 financial statements (February 1, 2003)

NASA PLANS TO ACHIEVE GREEN STATUS

#### Implement IFM System

NASA will complete full implementation of the IFM Core Financial module by achieving the following milestone:

- Successfully implement the IFMP Core Financial module at all nine field Centers and Headquarters (June 1, 2003) while continuing on schedule for implementing the remaining modules.

# EXPANDING ELECTRONIC GOVERNMENT

### CURRENT STATUS

OMB reports that NASA current status as “red” for e-government.  NASA has: completed all business cases for IT investment for FY 2002; made progress on its Enterprise Architecture (EA); begun to transition to the Information Technology Investment Portfolio System (I-TIPS); assessed IT security program and developed an action plan for correcting weaknesses; and is participating in seven E-gov initiatives (Geospatial Information One Stop, Recruitment One Stop, Enterprise HR Integration, E-authentication, Integrated Acquisition, and e-grants).

However, NASA’s business cases have historically been delivered late, NASA’s EA is not yet adequately integrated with its Capital Planning and Investment Control (CPIC) process, and NASA has weaknesses in some areas of security including program management and implementation at both the agency level and within Centers.  Additionally, there is inconsistent testing and evaluation of agency security effectiveness.

### NASA PLANS TO ACHIEVE YELLOW STATUS

- Capital planning and investment control process must include the necessary provisions to submit business cases that are complete and on time – September 2002.

- Revise remaining unsatisfactory 2002 business cases as identified by OIRA.

- Provide Exhibit 53 and IT business cases on time – September 2002.

- Create the FY 2004 President’s budget Information Technology schedule using the Information Technology Investment Portfolio System (I-TIPS) – September 2002.

- Per updated corrective action plans, complete GISRA IT security actions for all systems with security weaknesses – September 2002.

NASA PLANS TO ACHIEVE GREEN STATUS

#### Ensuring the Strategic Value of IT Investments, justify IT investments and integrate planning into agency decision-making processes and strengthen capital planning and investment control process

- Provide Exhibit 53 and IT business cases on time – September 2002.

- Complete updated corrective action plans for all systems with security weaknesses by September 2002.

- For the baseline IT projects, conduct evaluation and monitor program performance.  Metrics include; on average, operating within 90% of “OMB 300” cost, schedule, and performance targets by October 2002

- Plan and implement comprehensive Capital Planning and Investment Control (CPIC) process that integrates IT investments decisions with NASA’s Enterprise Architecture for selecting, managing, and evaluating IT investments by December 2002

- Collaborate with US Dept of Education and NSF in establishing a Federal e-Partnership Plan for delivering theme-based educational web campaigns in support of the President’s Education Agenda by July 2002.  Deliver and evaluate pilot campaign by December 2002.

- Establish an Agency level Enterprise Architecture office towards developing the next phase of NASA’s Enterprise Architecture.  Phase 1 to include major business operations by September 2002; Phase 2 adds 3 mission areas by July 2003.   This agency-level framework will address managing all IT investments and greater centralization of IT security functions.  Implement configuration management function by October 2002.

#### Achieving Internal Efficiency and Effectiveness by Leveraging Technology

- Transition and strengthen common IT infrastructure and shared services based on industry best practices to support “one NASA” - a move from distributed business processes to federated, shared services for accelerated IFMP deployment – February 2003.

- Ensure Agency participation as a partnering agency in implementing 3 OMB E-Government Initiatives (e-training, Enterprise HR Integration) - Ongoing

- For the eTraining initiative, provide support, technical assistance and advice to OPM.   Assist in the development of OPM’s initiative based on NASA’s development and implementation efforts on the “Solar” electronic training site.

#### Delivery of Information Services to the American Citizen

- Become the managing partner for a government-wide e-education project.  Submit e-education plan and business case for OMB approval by July 2002.

- E-Authentication – NASA has provided a full-time technical manager to GSA.  Chair the CIO Council Committee to oversee the project.

#### Improving Intergovernmental Efficiency through E-government

- Geospatial Information – NASA is partnering with Department of Interior to ensure our data products are compliant with the Geospatial Information One Stop initiative.

- EGrants

  - Coordinating the interagency activity under the initiative to expand previous efforts by NSF to pilot their electronic grant application system.  Partners include NSF/NIH/Agriculture/NOAA/ONR. On going activity

  - Initiated and led a pilot project to create an Internet portal to search across the Catalog of Federal Domestic Assistance and the FedBizOpps for grant programs and opportunities to be used in pre-populating the grant application.  Pilot to be integrated with E-Grants project for coordination of user training and testing by April 30, 2002.

  - NASA is also the lead on the group tasked by OMB to determine the best single identifier to be used across all Federal grant recipients by October 30, 2002.

Reduce the burden on Business through E-Government

- Integrated Acquisition – provide technical guidance and support for the government-wide initiative.  NASA led the technical development of FedBizOpps thru the early deployment of the NASA electronic posting system – NAIS.  Ongoing activity.

###### ACTIONS TO DATE

  - Developed an e-NASA strategy to provide a strategic framework for NASA e-government investments – July 2001

  - Assessed IT security program and developed corrective action plan - November 2001

  - Completed an assessment of NASA-wide IT infrastructure to support core business and mission requirements – January 31, 2002

  - Implementing an on-line Information Technology Investment Portfolio System (I-TIPS) and created an agency wide Information Technology call - March 15, 2002

  - Submitted to OMB all remaining “major” systems business cases for FY 2002 President’s budget submission  – March 15, 2002

  - Drafted Governance Paper for Agency discussion that incorporates strategic management of IT assets and robust implementation of CPIC – April 30, 2002

  - Developing plan and business case as the Managing Partner for a new cross agency initiative on E-education.

  - Initiated a series of Pilot Projects in the Agency that support the use of technology to more efficiently performs missions.  (Web-based collaboration tools, and internal and external portal pilots)

# BUDGET/PERFORMANCE INTEGRATION

CURRENT STATUS

OMB reports NASA’s status as “red” for budget/performance integration.  NASA has made efforts in recent years to move forward towards full cost budgeting and publish its budget justification and performance plan in a single document.  However, NASA has yet to implement full cost budgeting and management.  NASA’s performance planning is also inadequate to support performance budgeting.  OMB’s Spring Review will require all agencies, in concurrence with OMB, to select programs for evaluation in the President’s FY 2004 Budget and the criteria that will be used to evaluate those programs.

NASA has already taken the necessary steps to define its full cost budgeting, management, and accounting approaches in a formal Implementation Guide, which has been in use for planning purposes over the past two years, is assembling a representative full cost recast of its FY 2003 budget submission, and has initiated activities for formulating its FY 2004 Budget in full cost.  Also, NASA has been, for at least the past two budget cycles, using an integrated Agencywide budget formulation process with a single Agency-wide database to collect and review budget recommendations from the project level through the Center, Enterprise, and Agency management decision levels and ultimately produce all budget submission information.

NASA PLANS TO ACHIEVE YELLOW STATUS

Implement Full Cost Budgeting

- NASA will submit to OMB a full cost recast of its FY 2003 budget submission, in order to identify the changes attributed to the transition to full cost and act as a baseline for identifying programmatic-driven changes in the FY 2004 budget request.

- By September 2002, NASA will submit a five year, full cost budget for its FY 2004 budget request to OMB that distributes personnel, overhead, and related costs to the program level, for use by OMB in developing the FY 2004 President’s Budget.

Prepare for Performance Budgeting

- By May 15, 2002, NASA will reach agreement with OMB on the outline for a Performance Budget Document that integrates theme area goals, funding estimates, schedule, and related performance plan material.  This will be backed up by the appropriate Exhibit 300B’s; along with a list of programs to be covered through the OMB Spring Review and criteria for evaluating those projects based on the Administration's R&D criteria.

- By mid-June 2002, NASA will reach agreement with OMB on the formats to be used in the Performance Budget Document.

- By August 2002, a shared data file will be established as to where all formally cleared budget-process related documents to be used by OMB and NASA will be kept.

- By September 2002, NASA will submit to OMB an initial draft of its Performance Budget Document with

  - 100% of pre-defined Exhibit 300B’s,

  - at least the measures for 20% of the theme areas agreed to in the OMB Spring Review

NASA PLANS TO ACHIEVE GREEN STATUS

Implement Full Cost Management

- By December 2003 NASA will demonstrate that full cost budgeting, management, and accounting are routinely being used across the Agency and that program resources management decisions include the integrated consideration of personnel, overhead, and related programmatic costs and/or funding requirements.

Implement Performance Budgeting

- By February 2003, NASA will provide the completed Performance Budget Document for submission to Congress.

# PMA SCORECARD

Add line for "Agreed OMB-NASA Plan": all green

Replace "OMB Plan Score" with "OMB Progress (as of 31 March 2002)": oval colors stay the same