|  | NASA Procedural Requirements | NPR 8600.1 Effective Date: April 22, 2019 Expiration Date: April 22, 2024 |
| --- | --- | --- |

Subject: NASA Capability Portfolio Management Requirements

### Responsible Office: Office of Strategic Infrastructure

Table of Contents

Preface

P.1  Purpose

P.2  Applicability

P.3  Authority

P.4  Applicable Documents and Forms

P.5  Measurement/Verification

P.6  Cancellation

Chapter 1. Introduction

1.1  Background

Chapter 2. Managing Capability Portfolios

2.1  Capability Portfolios and Components

2.2  Capability Portfolios: Establishment, Strategic Management, and Termination

2.3  Key Tenets for Management of Capability Portfolios

2.4  Capability Portfolio Management Oversight

2.5  Reviews

Chapter 3. Capability Portfolio Requirements

3.1  Capability Portfolio Establishment

3.2  Capability Portfolio Strategic Management

3.3  Capability Portfolio Termination

Chapter 4. Capability Portfolio Roles and Responsibilities

4.1  Summary of Specific Roles and Responsibilities

Chapter 5. Dissenting Opinions and Tailoring Requirements

5.1  Process for Handling Dissenting Opinions

5.2  Tailoring Requirements

Appendix A. Definition of Terms

Appendix B. Acronyms

Appendix C. Capability Portfolio Commitment Agreement Template

Appendix D. Capability Portfolio Management Plan Template

Appendix E. NPR 8600.x Waiver Template

Appendix F. Capability Operational Readiness Level

Appendix G. References

List of Tables

Table 2-1 Capability Portfolio Governance and Authorities

Table 3-1 Approval for CPCA

Table 3-2 Approval for CPMP

Table 5-1 Waiver Approval for Capability Portfolios

Table C-1 Sample Capability Portfolio Commitment Agreement Activities Log

Table D-1 Sample Capability Portfolio Management Plan Activities Log

Table F-0 Capability Operational Readiness Level Summary

Table F-1 Capability Operational Readiness Level 1

Table F-2 Capability Operational Readiness Level 2

Table F-3 Capability Operational Readiness Level 3

Table F-4 Capability Operational Readiness Level 4

Table F-5 Capability Operational Readiness Level 5

Table F-6 Capability Operational Readiness Level 6

Table F-7 Capability Operational Readiness Level 7

List of Figures

Figure 2-1 Capability Portfolio Activities

Figure C-1 Capability Portfolio Commitment Agreement Title Page

Figure D-1 Capability Portfolio Management Plan Title Page

Figure E-1 CPM Waiver Template

Preface

P.1 Purpose

This document establishes the Capability Portfolio Management (CPM) requirements by which the National Aeronautics and Space Administration (NASA) establishes, strategically and centrally manages, and terminates capability portfolios (CPs) consistent with the governance model defined in NASA Policy Directive (NPD) 1000.0.

P.2 Applicability

This NASA Procedural Requirements (NPR) is applicable to NASA Headquarters and NASA Centers including Component Facilities and Technical and Service Support Centers. This language applies to the Jet Propulsion Laboratory, which is a Federally Funded Research and Development Center, other contractors, recipients of grants, and cooperative agreements or other agreements only to the extent specified or referenced in the applicable contracts, grants, or agreements.

This NPR applies to CPs approved by the Mission Support Council (MSC), whose charter is Section 6.4 of NPD 1000.3. The list of CPs is maintained by the Office of Strategic Infrastructure (OSI) Assistant Administrator and can be found under the “Other Policy Documents” tab in the NASA Online Directives Information System (NODIS) on the OSI menu at https://nodis-dms.gsfc.nasa.gov/NASA_Wide/restricted_directives/OSI_rep/OSI_list.cfm.

In this NPR, all mandatory actions (i.e., requirements) are denoted by statements containing the term “shall.” The terms: “may” or “can” denote discretionary privilege or permission, “should” denotes a good practice and is recommended but not required, “will” denotes expected outcome, and “are/is” denotes descriptive material.

In this directive, all document citations are assumed to be the latest version unless otherwise noted.

P.3 Authority

- National Aeronautics and Space Act, 51 U.S.C. § 20113(a).

- NPD 8600.1, NASA Capability Portfolio Management.

P.4 Applicable Documents and Forms

- NPD 1000.0, NASA Governance and Strategic Management Handbook.

- NPD 1000.3, The NASA Organization.

- NPD 1001.0, NASA Strategic Plan.

- NPD 2800.1, Managing Information Technology.

- NPD 2810.1, NASA Information Security Policy.

- NPR 1400.1, NASA Directives and Charters Procedural Requirements.

- NPR 1441.1, NASA Records Management Program Requirements.

- NPR 7120.5, NASA Space Flight Program and Project Management Requirements.

- NPR 7120.7, NASA Information Technology and Institutional Infrastructure Program and Project Management Requirements.

- NPR 7120.8, NASA Research and Technology Program and Project Management Requirements.

- NPR 8000.4, Agency Risk Management Procedural Requirements.

- NPR 8800.15, Real Estate Management Program.

- NPR 8820.2, Facility Project Requirements (FPR).

P.5 Measurement/Verification

Compliance with this NPR is verified through periodic benchmarks and assessments conducted under the authority of the OSI Assistant Administrator. Results from these benchmarks and assessments are communicated to the MSC, which ensures corrective actions are identified, implemented, and tracked to closure. The OSI Assistant Administrator has responsibility for regularly collecting and tracking measurement data on compliance.

P.6 Cancellation

None.

# Introduction

## Background

### The purpose of NASA CPM is to define, sustain, and ensure the effectiveness of the NASA capabilities needed to achieve NASA’s vision, mission, strategic goals, and objectives. This is achieved through strategic and centralized management that includes an Agency-wide strategy that is aligned (and periodically updated and realigned) with Agency needs and requirements aggregated across multiple Mission Directorates, Centers, programs, and projects.

#### CPM aims to identify and sustain an optimal mix of capabilities (e.g., in-house wind tunnels or rocket test stands) suited to meet Agency requirements and constraints, determine the most effective and efficient way to manage these capabilities (may include obtaining products and services from external capabilities), and determine where these capabilities (and the products and services they provide) should be located within the Agency.

#### CPM provides NASA with the ability to do the following:

- Evaluate, prioritize, and optimize a group of capability components within a CP.

- Identify and achieve needed capability, capacity, and quality for a CP based on Agency needs and requirements.

- Generate information for a CP to support Agency decision making.

- Evaluate whether resources based on customer needs and requirements are aligned with Agency strategy and priorities.

- Strategically and centrally manage portfolio capability components within the Agency in a way that balances the needs and demands of programs and projects and external partners.

- Analyze, characterize, and maintain cognizance of the capability domain.

#### A CP provides products and services to multiple programs and projects over a period that can span decades. While a product or service delivered (e.g., chemical propulsion test, wind tunnel test) can have defined goals, objectives, requirements, cost, a beginning, and an end, the CP delivering the product or service has no defined ending and will typically change and adapt over time to achieve greatest value for the Agency based on current and future programmatic needs and requirements.

#### Requirements for new, enhanced, and augmented capabilities within a portfolio are developed in response to current and future Agency requirements and strategic needs and in response to industry opportunities that are aligned strategically with Agency priorities.

### This document establishes the overarching requirements by which NASA will strategically and centrally manage certain functionally similar capability components and enabling infrastructure through CPs established and sustained by NASA consistent with the governance model contained in NPD 1000.0. The desired outcome of CPM is to:

- Meet current and future Agency requirements and strategic needs for the delivery of products and services to NASA programs and projects.

- Increase overall Agency efficiency and effectiveness.

- Eliminate unneeded redundancy.

- Leverage external capabilities when in the best interests of the Agency.

### The MSC initiates efforts to establish a CP, assigns CPs to sponsoring Mission Directorates, and adjudicates CP decisional reviews including the following:

- The transition from Establishment to Strategic Management activities.

- A significant change in the CP composition, management, or funding.

- The transition from Strategic Management to Termination activities.

### The MSC Chair serves as the Decision Authority for CP decisional reviews.

### CPs are collections of functionally similar capability components and enabling infrastructure (often geographically dispersed across multiple Centers) that are grouped to support strategic and centralized management, analysis, strategy development, decision making, and staffing level plans to meet NASA’s strategic needs, goals, and objectives. NASA services common requirements through CPs.

### Capability components are quantifiable; that is, they can be measured and prioritized. CPM processes support decision making by providing an awareness of the value, criticality, needed sustainment level, and overall resources (including the workforce) for portfolio capability components based on both current requirements and strategic needs. The need to manage assets within constrained resources creates a need to prioritize capability components.

# Managing Capability Portfolios

## Capability Portfolios and Components

### The MSC initiates efforts to establish a CP and designates a sponsoring Mission Directorate. Sponsoring Mission Directorates conduct activities to establish the CP. The MSC determines when a CP and its constituent capability components are ready for strategic and centralized management to meet customer requirements for products and services in the most effective and efficient way possible.

### A CP comprises specifically identified capability components that fall within the CP scope and their enabling infrastructure as defined in the Capability Portfolio Commitment Agreement (CPCA) and the Capability Portfolio Management Plan (CPMP).

### Assets may be excluded from the portfolio if they:

- Do not meet the minimum thresholds for the portfolio defined in the CPCA and the CPMP (e.g., a minimum test section area for wind tunnels).

- Are sustained “tools of the trade.”

- Are used in specialized applications (e.g., low Technology Readiness Level (TRL) for research and development).

### Capability components within a CP compose the underlying structure for delivering products and services to customers. They are typically distributed geographically across multiple Centers.

### The sponsoring Mission Directorate Associate Administrator (MDAA) selects a CP manager to strategically and centrally manage the CP.

#### The CP manager reports through the MDAA and should strive to maintain an Agency perspective and objectivity in decision making.

## Capability Portfolios: Establishment, Strategic Management, and Termination

A CP goes through three main sets of activities: Establishment, Strategic Management, and Termination.

### Establishment

When NASA leadership determines that it may be in NASA’s best interest to strategically and centrally manage a group of functionally similar capabilities in an integrated manner, the MSC initiates Establishment of a CP. Establishment activities include scoping the portfolio, designating its sponsoring Mission Directorate, identifying the portfolio capability components and enabling infrastructure of the portfolio, developing a management strategy and approach, designating a CP manager, and preparing the CPCA. A decisional review is held at the MSC to determine whether to formally establish a CP and transition to strategic and centralized management status, i.e., transition to Strategic Management activities.

### Strategic Management

The Strategic Management of a portfolio comprises key CPM activities that repeat throughout the portfolio’s lifespan. These activities include the following:

- Maintaining a strategy.

- Supporting the budget process.

- Securing funding.

- Evaluating portfolio capability components and assets for need of maintenance, upgrade, or divestment.

- Analyzing the capability domain inside and outside of NASA.

- Understanding capability supply and demand.

- Assigning customer requirements to capability components that can deliver products and services in accordance with the approach for making sourcing decisions.

- Assessing the health of the CP and its components.

- Identifying and implementing new capabilities and improvements to the CP to meet future needs.

### Termination

When NASA leadership determines that it is no longer in NASA’s best interest to strategically and centrally manage a CP in an integrated manner, the MSC initiates Termination of the portfolio. A Termination decision triggers the development of a Termination strategy and plan; the closing out of all activities associated with the management of the CP; and the reassignment of the portfolio’s capability components and enabling infrastructure to Center management in accordance with the Termination strategy.

### Figure 2-1 depicts activities of Establishment, Strategic Management, and Termination of a CP.

Figure 2-1 Capability Portfolio Activities

## Key Tenets for Management of Capability Portfolios

### Stakeholders and Governing Documents

#### CPs have multiple stakeholders, such as Centers, participating Mission Directorates, Office of the Chief Engineer (OCE) Technical Fellows, Office of the Chief Information Officer (OCIO), and multiple customers. The CP manager works collaboratively with stakeholders and customers to understand current and future demand for portfolio products and services and to balance the portfolio capability components and available Agency resources with that demand.

#### The CP manager works collaboratively with Centers that have portfolio capability components to develop and implement processes for strategically and centrally managing the CP and its components and to establish operational norms and thresholds. These processes, operational norms, and thresholds, which may differ from one CP to another, are documented in the CP governing documents, the CPCA and/or the CPMP. The CP manager manages and conducts all activities of the CP in accordance with the CPCA and CPMP.

#### Centers manage, maintain, and operate the portfolio capability components in accordance with the agreed-upon processes documented in the CPCA and CPMP.

### Ensuring Consistency with Capability Portfolio Plans and Direction

#### CP managers are responsible for ensuring that investments, divestments, acquisition strategies, procurements, or internal and external agreements that seek to either build or develop new capabilities or improve or divest of existing capabilities, whether NASA or NASA investment in a non-NASA capability, are consistent with the established and approved plans and direction of the CP.

#### CP managers are responsible for ensuring that acquisition strategies, procurements, or internal and external agreements that seek to obtain products and services from external capabilities or commit the use of capability components, are consistent with the established and approved plans and direction of the CP. (Products and services from external capabilities that are procurement line items included in a product delivery are excluded; e.g., a spacecraft build and test delivery.)

### Concurrence Processes, Engagement Points, and Methodologies

#### CP managers utilize concurrence processes to ensure consistency with established and approved plans and direction of the CP. Concurrence is required under specific thresholds, constraints, criteria, and/or circumstances. Guidelines for when concurrence should be obtained are established by engagement points. The concurrence processes, thresholds, constraints, criteria, circumstances, and engagement points are documented in the CPCA and the CPMP.

#### Defined engagement points are essential for ensuring concurrence takes place as early as possible in the MDAA, Center, and program and project management timelines, review cycles and decision-making processes. Early engagement points ensure that the plans of the MDAA, Center Director, JPL Lab Director, program manager, and project manager are consistent with CP-approved plans and directions.

#### Various methodologies may be applied to adapt the concurrence processes to engagement points. These methodologies are documented in the CPMP. The methodologies may be implemented at the individual strategy, procurement, or agreement level, or at an integrated Center level on a periodic basis.

#### The methodologies and engagement points for obtaining CP manager concurrence or non-concurrence may vary. For example, for competed missions a statement may be inserted into applicable Announcements of Opportunity (AOs) covering the requirements of this policy directive.

### Project Management and Capability Portfolios

#### The environment in which CPs exist is dynamic. The nature of customer requirements may change over time, requiring changes to the capability components that compose the portfolio. These changes may include improvements to existing components or the addition of new components. These changes are subject to:

- The concurrence processes and thresholds described in Section 2.3.3 and elsewhere in this NPR.

- Approval by the MSC at a decisional review if they exceed thresholds, criteria, and constraints for a significant change documented in the CPCA. (See Appendix C, Section 4.0.)

- Approval by the sponsoring MDAA if they exceed thresholds, criteria, and constraints for CP actions and changes documented in the CPMP. (See Appendix D, Section 3.5.)

#### Various means may be used to implement improvements to existing components or the addition of new components, ranging from tasks implemented under Center procedures to major projects implemented under Agency project management NPRs (i.e., NPRs 7120.5, 7120.7, 7120.8, and 8820.2). Projects may be proposed by the CP manager, a NASA program, or a Center.

- Based on capability gaps, the CP manager may propose projects, associated funding requirements and funding sources, and an implementing Center. Following approval by the sponsoring MDAA and/or the MSC (if required), the project is assigned to a Center for implementation. The implementing Center selects the project manager, coordinates with the CP manager on the appropriate governing NPR and on project requirements, and provides oversight of project implementation.

- A NASA program or Center may independently propose projects based on needs identified by a program or Center. When a proposed project is subject to CP concurrence processes based on thresholds defined in the CPMP, the CP manager and the program or Center work collaboratively early in the project Formulation Phase, and the CP manager provides guidance, requirements, and/or recommendations for the project culminating in the CP manager’s concurrence or non-concurrence on the proposed project’s plans related to the capability domain. A non-concurrence may be addressed through the appeal process documented in the CPMP. Following CP manager concurrence, approval by the sponsoring MDAA, and/or the MSC (if required), and approval by the project’s governing authority, the project is implemented under the authority of the NASA program or Center in accordance with the appropriate governing NPR.

### Capability Portfolio Sourcing Strategies and Sourcing Decisions

#### CP sourcing strategies and sourcing decisions play an integral role in CPM. The sourcing strategy and approach for making sourcing decisions are documented in the CPCA and the CPMP. In all cases, the CP sourcing strategy and sourcing decisions will be consistent with constraints established in awarded and existing contracts and agreements.

#### The sourcing strategy is a strategy for acquiring portfolio products and services through capabilities available in-house and through other agencies, vendors, partners, and academia. The sourcing strategy goal is to achieve an optimized portfolio that addresses Agency goals and objectives, supports the CP strategy, enables the CP’s strategic direction, and fully satisfies customer requirements.

- CP managers establish the sourcing strategy in collaboration with Mission Directorates and Centers. The sourcing strategy is described in the CPCA and documented in detail in the CPMP. The sourcing strategy may vary from one CP to another and within a CP.

- The sourcing strategy is periodically reevaluated to achieve an optimized portfolio including adjustments in response to changes in the products and services required by customers and changes in internal and external capabilities.

#### Sourcing decisions are the assignment of customer (NASA and external) requests to capability components. The approach for making sourcing decisions is described in the CPCA and documented in detail in the CPMP.

- Responsibilities for sourcing decisions may be delegated by the CP manager to Center Directors, the JPL Lab Director, MDAAs, program managers, or project managers. Any delegations are documented in the CPMP. Delegation of sourcing decisions may vary from one CP to another, within a CP, and for different types of customers (internal or external).

- The approach for making sourcing decisions is periodically reevaluated based on various changes, including changes to the sourcing strategy.

## Capability Portfolio Management Oversight

Each CP to which this NPR applies has the MSC as its governing council to provide management oversight. The authorities for managing a CP are defined in Table 2-1.

Table 2-1 Capability Portfolio Governance and Authorities

| Role / Responsibility / Function | Title / Council | Comments |
| --- | --- | --- |
| Approving authority to initiate Establishment of a CP | MSC |  |
| Decision Authority for Strategic Management and Termination decisional reviews | MSC Chair | Additional decisional reviews may be added at the MSC Chair’s discretion during Strategic Management. |
| Governing council | MSC |  |
| Governing documents |  | CPCA and CPMP |
| Approving authority for the CPCA | MSC Chair | Approval of the CPCA authorizes the transition to Strategic Management. The CPCA is revalidated or updated every five years or less. |
| Approving authority for the CPMP | Sponsoring MDAA | Timeframe for development of the CPMP is established in the CPCA. The CPMP is revalidated or updated every five years or less. |
| Decision Authority for significant change decisional reviews | MSC Chair | Significant change is defined by threshold(s), criteria, and constraints established in the CPCA. Approved significant changes may require updates to the CPCA and/or CPMP. |
| Selecting official for an advisory board | Sponsoring MDAA | MDAA may determine that existing board or council can perform the advisory function. |
| Manages the CP | CP Manager | May escalate decisions to sponsoring MDAA or the MSC Chair in accordance with thresholds. |

## Reviews

Reviews relevant to a CP comprise decisional reviews, CP reviews, and other reviews.

### Decisional Reviews

#### Decisional reviews are used to determine a CP’s readiness to proceed, approve significant changes to the CP, or terminate the CP. A decisional review occurs at three milestones:

- Transition from Establishment activities to Strategic Management activities (including approval of the CPCA).

- A significant change (“significant” is defined in the CPCA) in the composition, management, or funding of the CP.

- Transition from Strategic Management activities to Termination activities.

#### The MSC Chair may require additional decisional reviews.

#### The CP manager shall support and attend decisional reviews. In coordination with the sponsoring Mission Directorate, the CP manager prepares for a decisional review by determining the materials to be submitted to the MSC Chair to support the decision process. Materials used in support of decisional reviews are archived along with links to applicable Agency Web sites that archive MSC decision packages and MSC decision memorandums for decision reviews. (The archival method is documented in the CPMP.) These materials may include the following:

- Recommendations, assessments, and/or findings from the governing council (i.e., the MSC), the sponsoring Mission Directorate’s Directorate Program Management Council (DPMC), the CP review report(s), the CP manager, stakeholders, and Center Management Councils (CMCs). (See Section 2.5.2 for more information about CP review reports.)

- Relevant Agency priorities and roadmaps.

- Cost estimation reports.

- Relevant lessons learned.

- Documents requiring the MSC Chair’s signature (e.g., CPCA, CPMP).

#### The MSC Chair may also request additional documentation to support the decisional review.

#### The MSC Chair shall serve as the Decision Authority as specified in Table 2-1 and conduct CP decisional reviews at the MSC. The MSC Chair’s decision is based on consideration of a number of factors including but not limited to the following:

- Continued relevance of the CP and its components to the Agency’s vision and mission as defined by NPD 1001.0 and current Agency strategic implementation planning.

- Efficiency, effectiveness, and affordability with respect to the Agency’s resources.

- Agency, Mission Directorate, institutional, program, or project risks mitigated or managed by the CP.

- Evaluation of capability programmatic demand (aggregated program and project requirements) versus capability capacity (supply) available in-house and external to the Agency able to meet the capability requirements.

- Preparation and readiness to proceed and viability of proposed changes to the CP.

#### The results of a decisional review are documented in retrievable MSC documentation.

- If no changes are required following the decisional review, the MSC Chair signs applicable documents, which may include a decision memorandum, and the CPCA and/or CPMP.

- If changes are required, the documents are revised, all signatures are obtained, and the documents are resubmitted to the MSC Chair for final signature.

### Capability Portfolio Reviews

#### CP reviews are essential elements of managing and evaluating the performance of Agency capabilities. The sponsoring MDAA and CP manager are responsible for periodically evaluating the efficiency, effectiveness, and performance of the CP and its capability components. The evaluation focuses on how well the CP is aligned with Agency needs, how well commitments are being met, and how well management processes are being followed.

#### Evaluation of the performance of a CP occurs at different levels among different stakeholders. In developing the review requirements, the sponsoring MDAA and CP manager should consider the need for internal reviews conducted by the CP manager, sponsoring Mission Directorate reviews conducted by the DPMC; advisory board reviews, stakeholder reviews, and/or external reviews independently performed by outside organizations.

#### CP managers identify the reviews appropriate for each CP in coordination with the sponsoring MDAA and the MSC Chair to ensure the continued relevance (alignment with Agency vision and mission), performance, effectiveness, and affordability of the CP.

#### Planned CP reviews are identified in the CPCA and CPMP. The approach to conducting the reviews and the review team structure are documented in the CPMP.

### Other Reviews

The MSC Chair evaluates the performance of CPs against defined goals and objectives. Evaluations may be implemented through the MSC CPM Annual Review, reports from the MSC, and Agency-level reviews, such as the Agency Baseline Performance Review (BPR).

# Capability Portfolio Requirements

## Capability Portfolio Establishment

### Initiate Effort to Establish a Capability Portfolio

#### The MSC shall initiate the effort to establish a CP. The MSC is responsible for ensuring that the start of a new CP is in line with the Agency’s vision and mission as defined in NPD 1001.0. The decision to initiate the effort will be documented in an MSC decision memorandum.

#### The MSC shall appoint the sponsoring MDAA for the CP.

#### The sponsoring MDAA may allocate discretionary funds or utilize funding specifically designated by the Office of the Administrator to conduct activities associated with establishing a CP. These funds may be allocated by the MDAA to specific Centers, managed internally, or used to fund external studies associated with the potential CP.

#### The Office of the Chief Information Officer (OCIO) shall advise the MSC whether a CP or part of a CP is inherently information technology (mission, corporate, or industrial control systems).

### Establishment Activities

#### The sponsoring MDAA shall:

- Select a CP manager to manage the effort to establish the CP (i.e., initiate scoping and initial planning). If the CP manager resides at a Center, the MDAA coordinates the selection of the CP manager with the Center Director.

- Provide to the CP manager, in writing, the goals and objectives, the capability domain and preliminary scope, and the constraints of the CP as part of Establishment activities. This may be in the form of a one-page document signed by the MDAA, budget guidance, or other document as needed for the type, size, and complexity of the CP.

- Establish a management and governance structure for each CP sponsored by the Mission Directorate.

- For each CP sponsored by the Mission Directorate, coordinate with the CP manager to develop and annually update a five-year CP budget commensurate with CP goals and objectives, CP operational norms, and funding responsibilities (one or more funding models), and establish a process to secure the level of funding needed to operate and sustain the CP and its components.

#### The CP manager shall conduct Establishment activities working collaboratively with the Centers that operate components of the proposed portfolio and with the sponsoring and participating Mission Directorates. These activities include the following:

- Developing a strategy for managing the CP.

- Creating initial plans for managing the portfolio.

- Finalizing the scope of the CP.

- Developing financial and resource management processes that may include a customer charging methodology, an estimate of and process for determining the TCO for the portfolio and its capability components, a process to identify annual funding requirements, and a process to establish and allocate any resources.

- Establishing the sourcing strategy and approach for making sourcing decisions for the CP.

- Defining operational norms and thresholds.

#### The CP manager will develop a strategy for managing the portfolio that includes the following:

- Identifying the environment in which the CP will be managed.

- Identifying the CP customers, stakeholders, and partners.

- Identifying constraints on the CP and opportunities available to the portfolio.

- Identifying areas of high risk for the portfolio.

- Developing strategic themes or focus areas for the portfolio, their alignment with NASA’s strategic goals, and their associated value.

- Developing a strategic direction for evolution of the portfolio that capitalizes on strengths, identifies investment and divestment priorities, and addresses weaknesses, gaps, and risks. This includes identifying the following when possible:

- Strategic CP investments, divestments, improvements, and replacements.

- Technology development.

- Estimated resource requirements.

#### The CP manager will create an initial plan for managing the CP that includes the following:

- Goals, objectives, and targets for the CP.

- Products and services and the level of services to be provided by the CP to NASA programs and projects and external customers.

- The CP’s governance and management structure and approach.

- The organizational structure, roles, and responsibilities.

- How performance of the CP will be evaluated, including identifying performance metrics.

- Thresholds, criteria, and constraints that determine the need for a decisional review to approve CP significant changes or that determine the need for review by the sponsoring MDAA to approve CP actions and changes.

- The review approach.

- The approach to data management at the CP level.

- Any documentation needed (such as a CP risk management plan).

#### The detailed planning is completed as part of the Strategic Management activities. The CP manager also identifies the timeframe for completion of detailed planning and approval of the CPMP. (See Section 3.2 for information on detailed planning and the CPMP.)

#### Using the MDAA-provided goals and objectives, capability domain and preliminary scope, and constraints of the CP, the CP manager will finalize the CP scope and identify the specific collection of functionally similar site-specific capability components and enabling infrastructure that comprise the CP. This includes gaining an understanding of the capabilities associated with the portfolio that exist within NASA, other agencies, industry, and academia, as well as characterizing capabilities within the domain that will not be included in the portfolio. It also includes conducting an analysis to understand current and future needs and requirements for the CP’s products and services aggregated across all Mission Directorates, programs, and projects. The CP manager will do the following:

- Develop and maintain an inventory for the CP that includes all portfolio capability components and the products and services delivered. The inventory should include detailed information, such as workforce (Full-Time Equivalent (FTE)/Work-Year Equivalent (WYE)), critical skills and competencies, assets, equipment, management and operational processes, and technologies in development or needed to address capability gaps or improvements.

- Establish and maintain a scheme for classification and decomposition of the CP that facilitates planning, control, cost analysis, and other analyses, such as identification of capability gaps and excess capacity. For example, the assets/capabilities in the Space Environments Testing (SET) portfolio might be broken down into thermal vacuum chambers, vibration tables, acoustic cleanrooms, and other assets.

- Establish and maintain a description and inventory of the “core capability,” which is the minimum workforce (FTE/WYE), competencies, assets, equipment, processes, and technologies below which NASA will assume unacceptable risk to current and future missions.

- Develop and maintain a catalog of external sources used by the CP to deliver products and services.

- Characterize the insight role for capabilities within the domain that are not included in the portfolio. Insight may include identifying relevant capabilities outside of NASA but within the United States and determining the level of detail needed on each identified capability, such as the availability to NASA customers and the type and cost of products and services provided. The insight needed may vary from one CP to another.

#### The CP manager will estimate the TCO for the portfolio and its capability components; support the sponsoring MDAA in developing and annually updating a five-year CP budget commensurate with CP goals and objectives, CP operational norms, and funding responsibilities (one or more funding models) for the CP; and establish a process to secure the level of funding needed to operate and sustain the CP and its components.

#### In coordination with Centers and the sponsoring and participating MDAAs, the CP manager will develop financial and resource management processes that may include the following:

- A transparent customer charging methodology for products and services. This includes a description of cost items, categories, and the structure used for customer charging.

- A process to determine the past and current TCO for the CP and its components, including identification of the cost elements necessary to meet the needs of the CP. The TCO is broken down by customer and Mission Directorate contribution. This includes program direct, external customer reimbursable, Center Management and Operations (CM&O), and CP direct funding (e.g., the Rocket Propulsion Testing (RPT) portion of total funding).

- A process to identify annual funding requirements based on the CP TCO and investment plans, update the budgets, and establish and update the CP funding model(s).

- A process to establish and allocate any resources provided annually to portfolio capability components to achieve the needed Capability Operational Readiness Level (CORL) and to maintain those capability components. (See Appendix F for CORL information.)

#### The CP manager will establish a sourcing strategy and the approach for making sourcing decisions in collaboration with the sponsoring and participating MDAAs, Center Directors, and the JPL Lab Director with portfolio capability components at their Centers.

#### The CP manager will collaboratively define the operational norms between the CP manager, programs and projects (as appropriate), and Centers and establish any thresholds necessary to enable effective strategic and centralized management of the portfolio and enable efficient operations of portfolio capability components. (Operational norms and thresholds are documented in the CPCA and CPMP.)

#### The sponsoring MDAA serves as the selecting official for a CP advisory board if it is determined that such a board is needed for a CP. The board should include representation from each Center and participating Mission Directorate utilizing services provided by the CP, the sponsoring Mission Directorate, and the Centers that host portfolio capability components. If the CP is inherently information technology, the board should also include representation from OCIO.

#### In support of CPM, the sponsoring and participating MDAAs shall assign a Mission Directorate CP point of contact (POC) for each CP.

#### In support of CPM, Center Directors and the JPL Lab Director:

- Shall appoint Center CP POCs for the CP(s) that include components at the Center.

- Will support CP managers in defining operational norms between the CP manager, program and project managers (as appropriate), and Centers and in establishing any thresholds necessary to enable efficient operations of portfolio capability components at the Center. (Operational norms and thresholds are documented in the CPCA and CPMP.)

- Will support CP managers in establishing the metrics necessary for strategic insight and management of the portfolio capability components at the Center. The metrics are documented in the CPCA and CPMP.

- Will support the CP manager in developing financial and resource management processes.

- Will coordinate with the CP manager and other key stakeholders to establish agreement on charging methodologies for the CP. The charging methodologies are documented in the CPCA and CPMP.

- Will support the CP manager in developing the sourcing strategy and approach to making sourcing decisions.

#### In support of CPM, the Chief Information Officer shall:

- As the Information Technology Council (ITC) Chair and Decision Authority, review and approve CP investments and divestments in information technology capabilities that are governed under NPD 2800.1 and NPD 2810.1.

- Appoint OCIO CP POCs for CP(s) that are determined by the MSC to be inherently information technology.

#### In support of CPM, the Chief Financial Officer shall support Mission Directorates and CP managers in establishing and validating CP funding model(s).

### Capability Portfolio Commitment Agreement

#### The CPCA is an agreement between the MSC Chair and the sponsoring MDAA and is necessary for the CP to transition from Establishment to Strategic Management. The content of the initial CPCA reflects the maturity of the CP at the beginning of Strategic Management. Prior to approval of the CPCA, the sponsoring MDAA coordinates with the MSC Chair, any participating MDAAs, and any Center Directors and the JPL Lab Director that have portfolio capability components that reside at their Centers to ensure their commitment to support the CP.

Table 3-1 Approval for CPCA

| MSC Chair | Approves |
| --- | --- |
| Sponsoring MDAA | Recommends |
| Participating MDAAs | Concur |
| Center Directors and the JPL Lab Director with portfolio capability components | Concur |
| Center Directors and the JPL Lab Director without portfolio capability components | Informed |
| Chief Information Officer (when the MSC has determined that the CP is inherently information technology) | Concurs |
| Note: Non-concurrences that cannot be resolved at the CP manager level are elevated to the sponsoring MDAA level. Non-concurrences that cannot be resolved at the sponsoring MDAA level are elevated to the MSC Chair. |

#### The sponsoring MDAA with support from the CP manager shall develop a CPCA. The CPCA documents the results of the Establishment activities and includes but is not limited to the following: (Required CPCA content is indicated.)

- CP goals and objectives. (Required)

- Products and services to be provided. (Required)

- Capability domain and CP scope. (Required)

- Plan for achieving CP goals and objectives. (Required)

- Metrics for evaluating overall CP performance. (Required)

- CP authorities and governance and organizational structure. (Required)

- Timeframe for completion of CPMP. (Required)

- Operational norms (in as much detail as possible).

- Thresholds, criteria, constraints, and circumstances (in as much detail as possible) including thresholds for a significant change decisional review.

- Estimated cost for the CP to operate. (Required)

- Approach for securing funding.

- Funding model(s) (in as much detail as possible). (Required)

- CP sourcing strategy and approach for making sourcing decisions (in as much detail as possible). (Required)

- High-risk areas. (Required)

- Internal and external dependencies and agreements. (Required)

- Planned reviews. (Required)

#### The CPCA may take the form shown in the template provided in Appendix C or any other form as appropriate for the type, size, and complexity of the CP.

#### The sponsoring MDAA recommends the CPCA for approval to the MSC Chair. Center Directors and the JPL Lab Director who host portfolio capability components at their Centers and participating MDAAs shall concur or non-concur on the CPCA. A written explanation for a non-concurrence should be provided.

#### The Chief Information Officer shall concur or non-concur on the CPCA if the MSC has determined that the CP is inherently information technology. A written explanation for a non-concurrence should be provided.

#### The MSC Chair shall approve or disapprove the CPCA and provide rationale.

#### The CP manager shall revalidate or update the CPCA every five years. Updates may occur more frequently if there are significant changes as defined in the CPCA and as determined by the CP manager or sponsoring MDAA. The updated CPCA is reviewed and approved using the same process as the original.

### Approval to Transition to Strategic Management

#### The MSC Chair shall conduct a decisional review to determine approval for a CP to transition to Strategic Management activities. The decisional review is held at the MSC.

- If Establishment planning is not sufficient to approve the transition, the MSC Chair may direct the CP manager to continue the Establishment effort or to modify the Establishment plans based on identified weaknesses.

- If the MSC Chair determines that concepts for the potential CP do not meet minimum requirements, a decision to discontinue the Establishment effort may be made.

- If the Establishment planning is sufficient, the MSC Chair authorizes the CP to transition to Strategic Management activities.

#### As part of the decisional review, the MSC Chair reviews the CPCA and any other relevant data requested to ensure that the CP objectives are aligned with the Agency’s vision and mission as defined by NPD 1001.0.

#### The decision is documented in retrievable MSC documentation. The documentation should include the authorization to transition to Strategic Management activities, any other decisions made, and any actions assigned. If no changes are required following the decisional review, the MSC Chair signs the CPCA. If changes are required, the CPCA is revised, all signatures are obtained, and the document is resubmitted to the MSC Chair for final signature.

## Capability Portfolio Strategic Management

### Strategic Management Activities

#### Developing and Implementing Activities and Associated Processes

The CP manager shall develop processes and conduct Strategic Management activities for the CP. Once developed, these activities and associated processes are documented in the CPMP and are repeated throughout the lifespan of the CP. (See Section 3.2.2.) Strategic Management activities include the following:

- Update, maintain, and implement processes developed as part of the Establishment activities:

- Maintain the overall CP strategy.

- Complete detailed plans for managing the portfolio.

- Update the scope of the portfolio, including updating capability inventories and catalogs and maturing the understanding of customer requirements. (See Section 3.2.1.2.)

- Refine and maintain the estimated annual cost, funding models, and processes for securing funding. (See Section 3.2.1.5.)

- Mature, adjust, and implement the sourcing strategy and approach for making sourcing decisions. (See Section 3.2.1.3.)

- Develop and implement processes for strategically and centrally managing and maintaining oversight of the CP’s capability components; understanding and influencing current and future Agency demand; evaluating CP performance; and managing change, improvement, and evolution of the CP. (These processes are described in Sections 3.2.1.4, 3.2.1.6, and 3.2.1.7, respectively.)

#### Understanding Customer Requirements

The CP manager will develop and maintain a process for understanding and influencing current and future Agency demand for CP products and services to ensure the ability and capacity (through the in-house and external sources) to meet those demands and to achieve Agency objectives in fostering and servicing demand. This process may include activities to:

- Establish and maintain a constructive relationship with customers (e.g., programs, projects, and external customers that need products and services) and other stakeholders (e.g., Mission Directorate CP POCs, Centers operating portfolio capability components, the CIO, and Technical Fellows).

- Coordinate with customers and other stakeholders (NASA and external) to identify:

- Sources of demand, demand characteristics (such as demand confidence, constraints, and purposes of need), and strategic requirements to inform both CP strategy and operational plans.

- New or improved portfolio capability components that are needed to meet requirements for products and services.

- Maintain communication and liaison with customers to assure best fit of capabilities (combination of in-house and external) with customer needs and requirements.

- Periodically collect and aggregate Agency requirements to create, maintain, and confirm a CP demand baseline and analyze and prioritize requirements from sponsoring and participating MDAAs, Center Directors and the JPL Lab Director, program and project managers (as appropriate), external customers, and other stakeholders, such as Technical Fellows and groups performing research and innovation.

#### Managing the Sourcing Strategy and Sourcing Decisions

The CP manager will strategically and centrally manage the sourcing strategy and sourcing decisions for assigning customer requests to capability components available in-house and through other agencies, vendors, partners, and academia. (See Appendix D for detailed information on the sourcing strategy and the approach for making sourcing decisions, including applicable considerations.) This may include the following:

- Assessing historical demand and projected future needs to define demand patterns for the purpose of understanding and predicting the impact of mission needs on the portfolio and informing the sourcing strategy.

- Maturing the sourcing strategy through analysis and prioritization based on value, mission criticality, customer and source risk, and overall Agency cost implications.

- Surveying the capabilities of external sources.

- Periodically reevaluating and adjusting the sourcing strategy in response to changes in the products and services required by customers and changes in internal and external capabilities (e.g., when external sources develop capabilities for products and services that are equal to or better than those available in-house).

- Periodically reevaluating and adjusting the approach for making sourcing decisions in accordance with changes to the sourcing strategy.

- Making sourcing decisions in accordance with the defined approach.

#### Overseeing the Capability Portfolio and Its Components

The CP manager will strategically and centrally manage and maintain oversight of the capability components within the portfolio to achieve the right mix of capabilities, capacity, and levels of service (LoS) and to ensure that the CP achieves the capacity needed (for individual components and the entire portfolio) to meet customer needs and requirements in a cost-effective and timely manner. The CP manager will:

- Communicate with CP POCs of Centers that deliver products and services to provide needed and effective guidance, communicate CP strategic direction, and maintain awareness of local tactical plans.

- Maintain aggregated, integrated operational plan (portfolio level) for delivery of products and services that translate and align with the CP overall strategy and maintain oversight of products and services delivered.

- Establish, maintain, and update processes and guidelines for developing cost estimates for delivering products and services to customers.

- Conduct oversight of financial resources.

- Establish reporting requirements for all capabilities within the CP. Reports may include operational plans for delivery of products and services at the capability component level, actual deliveries of products and services, maintenance and improvement investments and divestments, unscheduled maintenance, corrective actions, facility utilization, risks, and performance metrics.

- Establish a process for maintaining cognizance and insight into capability components within the capability domain that are not included in the portfolio.

- Facilitate value-added consistency and standardization across capability components in developing processes for providing products and services (e.g., customer service agreements, training procedures).

- Establish operational norms for adjusting the CORLs of portfolio capability components and their LoS based on targeted Agency capacity and demand.

- Establish operational norms for approving alternate uses of portfolio capability components in support of innovation and new customers.

- Work collaboratively with Centers to establish and maintain appropriate staffing levels and identify the competencies needed for portfolio capability components.

#### Estimating the Annual Cost and Securing Funding

The CP manager will refine and maintain the estimate of the TCO for the portfolio and its capability components, support the MDAA in updating the CP funding model(s), and coordinate efforts to secure the appropriate level of funding to operate and sustain the portfolio. (The initial annual cost estimate, funding model(s), and processes for securing funding are developed as part of the Establishment activities. (See Section 3.1.2.1 (d).) Securing funding may include the following:

- Providing input relative to CP strategy and priorities into strategic planning guidance and program resource guidance documents.

- Ensuring that planning and budgeting and the investments and divestments described are aligned with NASA mission needs and requirements.

- Collaborating with Centers to identify and resolve budget issues.

#### Evaluating Capability Portfolio Performance

The CP manager will assess the performance of the CP and its components and identify changes needed to CP strategy, objectives, processes, products, and services to improve reliability, quality, performance, and cost effectiveness. The CP manager will:

- Identify CP risks and develop and ensure implementation of actions to mitigate risks.

- Analyze planned versus actual CP performance and identify trends. Collaborate with Centers to determine underlying causes of performance problems and identify, prioritize, and ensure implementation of changes needed to address those causes.

- Conduct and support planned reviews. (See Sections 2.5.2 and 3.2.3.2.)

- Obtain additional advice, input, and recommendations from stakeholders, such as Mission Directorate, OCIO, Center CP POCs, and a CP advisory board.

#### Managing Change, Improvement, and Evolution

The CP manager will strategically and centrally manage change, improvement, and evolution of the CP and its components to continuously align products and services delivered by the CP with changing Agency needs and requirements and to support established objectives and targets for the CP. This may include:

- Analyzing requirements and identifying and proposing strategic investments and divestments to address capability gaps, advancements in technologies, needs for capability enhancements, opportunities, threats, and new and changed products and services needed to support customers.

- Developing and maintaining a CP Strategic Development Plan that provides a detailed description of the needed future state for the portfolio capability components and the processes for delivering products and services. This plan:

- Defines the process and approach to evolve the set of portfolio capability components to better support current and future customers and requirements.

- Informs the development and prioritization of changes to be implemented.

- Serves as a guide for the assessment of infrastructure improvements and associated investments including modernization, upgrades, and new construction.

- Addresses funding sources.

- Addresses the scope of projects that may be needed.

- Addresses the strategic divestments and investments that need to be aligned with Center Master Plans and the Agency Master Plan.

- Evaluating the financial impact of proposed changes to the CP and its components. Changes may include:

- Products and services provided.

- Level of sustainment for each portfolio capability component.

- Targeted Agency capacity.

- Investments and divestments.

- Coordinating and guiding policy and design and development efforts to facilitate value-added consistency and standardization across portfolio capability components and investments in systems, architectures, and technologies. Examples include equipment specifications, interface control, and personnel certifications.

- Supporting decisional reviews for significant changes that exceed the thresholds or meet the criteria and constraints defined in the CPCA.

- Representing the CP to Agency management and councils and effectively providing and presenting information that supports strategic decision making.

#### Providing Concurrence or Non-Concurrence

- The CP manager shall concur or non-concur (and provide a written explanation for a non-concurrence):

- On investments, divestments, acquisition strategies, procurements, or agreements that seek to either build or develop new capabilities or improve or divest of existing capabilities, whether NASA or NASA investment in a non-NASA capability, that fall within the capability domain and thresholds defined in the CPMP. Various methodologies may be applied to adapt this policy to engagement points for CPM for ensuring consistency. These methodologies will be described in the CPCA and/or the CPMP.

- On acquisition strategies, procurements, or agreements to obtain products and services from external capabilities that fall within the capability domain and circumstances defined in the CPCA and CPMP. This may be done at the individual strategy, procurement, or agreement level or at an integrated Center level on a periodic basis.

- On internal (e.g., between a Center and programs, projects, and other Centers) or external (e.g., Space Act, international) implementation agreements that commit the use of CP capability components that fall within the thresholds defined in the CPMP. This may be done at the individual strategy, procurement, or agreement level or at an integrated Center level on a periodic basis.

- On significant changes to the CP baseline plan to commit the use of CP capability components that fall within the thresholds defined in the CPMP.

- On operational changes to a capability component within the CP that fall within the thresholds defined in the CPMP.

- On terminating plans for investments, divestments, and improvements that previously received CP manager concurrence.

- The CP manager shall also evaluate and make recommendations for proposals to be provided to Agency leadership that involve changes to the capability domain and fall within thresholds defined in the CPMP.

- The CP manager will also approve or disapprove alternate uses of CP capability components in accordance with the approach defined in the CPMP.

#### Sponsoring Mission Directorate Activities

In support of CPM, the sponsoring Mission Directorate shall:

- In coordination with the CP manager, update funding model(s) as needed for each CP sponsored by their Mission Directorate.

- Provide MDAA resources for the strategic and centralized management of each CP sponsored by their Mission Directorate and its components as defined in the CPCA and CPMP and ensure that resources are sized to meet the established goals and objectives.

- Ensure sponsored CP capabilities are:

- Available to deliver products and services to the Agency in support of programs and projects.

- Consistent with NPD 1001.0.

- Functioning within established budget, schedule, and cost constraints.

#### Sponsoring and Participating Mission Directorate Activities

In support of CPM, sponsoring and participating Mission Directorates:

  - As an integral part of established timelines, review cycles, and decision-making processes, shall obtain concurrence from the CP manager:

- On investments, divestments, acquisition strategies, procurements, or agreements that seek to either build or develop new capabilities or improve or divest of existing capabilities, whether NASA or NASA investment in a non-NASA capability, that fall within the capability domain and thresholds defined in the CPMP.

- On acquisition strategies, procurements, or agreements to obtain products and services from external capabilities that fall within the capability domain and circumstances defined in the CPCA and CPMP.

- On operational changes to a capability component within the CP that fall within the thresholds defined in the CPMP.

  - Shall obtain and document the CP manager’s evaluation of and recommendations for proposals to be provided to Agency leadership that involve changes to the capability domain and fall within thresholds defined in the CPMP.

  - Will provide the MDAA’s near and long-term strategic requirements associated with planned programs and projects that involve the capability domain.

- Will support CP assessments and analyses as specified in the CPMP. Examples include providing information to support development of assessments and analyses, such as demand baseline requirements, annual demand forecast analyses, and the CP Strategic Development Plan.

Will provide Mission Directorate funding in accordance with the funding model(s) defined, documented, and agreed upon in the CPCA and CPMP, once approved.

#### Center Director and JPL Lab Director Activities

In support of CPM, Center Directors and the JPL Lab Director:

  - As an integral part of the Center’s established timelines, review cycles, and decision-making processes, shall obtain concurrence from CP managers:

- On investments, divestments, acquisition strategies, procurements, or agreements that seek to either build or develop new capabilities or improve or divest of existing capabilities, whether NASA or NASA investment in a non-NASA capability, that fall within the capability domain and thresholds defined in the CPMP.

- On acquisition strategies, procurements, or agreements to obtain products and services from external capabilities that fall within the capability domain and the circumstances defined in the CPCA and the CPMP.

- When the Center proposes any significant changes to the CP baseline plan to commit the use of portfolio capability components that fall within the thresholds defined in the CPMP or, if a CP baseline plan is not used, prior to formalizing internal or external implementation agreements that commit the use of portfolio capability components that fall within the thresholds defined in the CPMP.

- On operational changes to a capability component within the CP that fall within the thresholds defined in the CPMP.

  - Shall obtain and document CP manager’s evaluation of and recommendations for proposals to be provided to Agency leadership that involve changes to the capability domain and fall within thresholds defined in the CPMP.

  - Shall obtain concurrence or non-concurrence from CP managers on the termination of plans for investments, divestments, and improvements that previously received CP manager concurrence.

  - Will manage, operate, and maintain the Center’s CP components and enabling infrastructure consistent with strategic guidance included in approved CPCAs and CPMPs that may include the funding level agreed upon by the CP manager for delivery of products and services to customers and approaches for adjusting the CORLs of portfolio capability components and their LoS.

  - Will obtain approval from the CP manager for alternate uses of portfolio capability components in accordance with the approach defined in the CPMP.

Will evaluate and assess all work related to the CP that operates at the Center. Work to be evaluated and assessed includes but is not limited to the following:

- Cost estimates for planned delivery of products and services.

- Technical, cost, and schedule performance metrics.

- The condition of portfolio capability components.

- Risks that have the potential to impact the CP and its constituent components.

- Planned improvements and investments.

- Planned divestments.

Will provide the Center evaluation and assessment findings and recommendations to the CP manager in support of CP manager, MSC, and MSC Chair reviews of the CP.

Will develop cost estimates for planned delivery of products and services in accordance with cost estimating processes and guidelines defined in the CPMP and CP baseline plan (if used).

Will provide Center resources in accordance with the funding model(s) defined, documented, and agreed upon in the approved CPCA and CPMP.

Will manage and implement investment projects at the Center that are intended to improve existing portfolio capability components or add new capability components to a CP. Oversee and manage projects and tasks assigned to the Center that affect the CP, improve portfolio capability components, develop new capability components for the CP, and divest of portfolio capability components.

Will provide Center-level reports, assessments, and data for portfolio capability components that reside at the Center to support CP assessments and analyses as specified in the CPMP. Examples include providing information to support development of assessments and analyses, such as demand baseline requirements, annual demand forecast analyses, and CP Strategic Development Plans.

Will support CP managers in defining operational norms between the CP manager, program and project managers (as appropriate), and Centers and in establishing the thresholds necessary to enable efficient operations of portfolio capability components at the Center. (Operational norms and thresholds are documented in the CPCA and the CPMP.)

Will support CP managers in establishing the metrics for each portfolio capability component at the Center as defined in the CPMP.

#### Program and Project Manager Activities.

In support of CPM, program and project managers:

  - As an integral part of established timelines, review cycles, and decision-making processes, shall obtain concurrence from the CP manager:

- On investments, divestments, acquisition strategies, procurements, or agreements that seek to either build or develop new capabilities or improve or divest of existing capabilities or facilities, whether NASA or NASA investment in a non-NASA capability, that fall within the capability domain and thresholds defined in the CPMP.

- On acquisition strategies, procurements, or agreements to obtain products and services from external capabilities that fall within the capability domain and the circumstances defined in the CPCA and CPMP.

- When the program or project proposes any significant changes to the CP baseline plan to commit the use of portfolio capability components that fall within the thresholds defined in the CPMP or, if a CP baseline plan is not used, prior to formalizing internal or external implementation agreements that commit the use of portfolio capability components that fall within the thresholds defined in the CPMP.

- On operational changes to a capability component within the CP that fall within the thresholds defined in the CPMP.

  - Shall obtain concurrence or non-concurrence from the CP manager on the termination of plans for investments, divestments, and improvements that previously received CP manager concurrence.

  - Shall obtain and document CP leadership’s evaluation of proposals to be provided to Agency leadership that involve changes to the capability domain and fall within thresholds defined in the CPMP.

  - Will support CP assessments and analyses as specified in the CPMP. Examples include providing information to support development of assessments and analyses, such as demand baseline requirements, capability investments and divestments, and annual demand forecast analyses.

  - Will support CP managers in defining operational norms between the CP manager, program and project managers (as appropriate), and Centers and in establishing the thresholds necessary to enable efficient operations of portfolio capability components at the Center. (Operational norms and thresholds are documented in the CPCA and CPMP.)

#### OCIO Activities

In support of CPM, the OCIO shall:

- As the ITC Chair and Decision Authority, review and approve CP investments and divestments in information technology capabilities that are governed under NPD 2800.1 and NPD 2810.1.

- Support CP assessments and analyses as specified in the CPMP for CPs that are determined by the MSC to be inherently information technology.

#### Chief Financial Officer Activities

In support of CPM, the Chief Financial Officer shall work with the Office of the General Counsel to support Mission Directorates and CP managers in updating and validating CP funding model(s) as needed.

### Develop the Capability Portfolio Management Plan

#### The CPMP is an agreement between the sponsoring MDAA and the CP manager that details how the CP will be managed. It is used by the DPMC and the MSC to determine if the CP is fulfilling its requirements. The CPMP is developed and approved as shown in Table 3-2 within the timeframe specified in the CPCA. Prior to approval of the CPMP, the CP manager coordinates with the sponsoring MDAA, any participating MDAAs, and any Center Directors and the JPL Lab Director that have portfolio capability components that reside at the Centers to ensure their concurrence. Once approved, the CP and its capability components are strategically and centrally managed as described in the CPMP.

Table 3-2 Approval for CPMP

| MSC Chair | Informed |
| --- | --- |
| Sponsoring MDAA | Approves |
| Participating MDAAs | Concur |
| CP manager | Recommends |
| Center Directors and the JPL Lab Director with CP capability components | Concur |
| Center Directors and the JPL Lab Director without CP capability components | Informed |
| Chief Information Officer (when the MSC has determined that the CP is inherently information technology) | Concurs |
| Note: Non-concurrences that cannot be resolved at the CP manager level are elevated to the sponsoring MDAA level. Non-concurrences that cannot be resolved at the sponsoring MDAA level are elevated to the MSC Chair. |

#### The CP manager shall develop a CPMP. The CPMP documents the results of the Strategic Management activities and includes, but is not limited to, the following: (Required CPMP content is indicated.)

- Goals and objectives. (Required)

- Customers, beneficiaries, and stakeholders. (Required)

- Authority, governance, and management structure. (Required)

- Capability domain, CP scope, and products and services. (Required)

- Scheme for classification and decomposition of the portfolio.

- Operational norms between the CP manager, Centers and the JPL Lab Director, and programs and projects. (Required) Examples include:

- Thresholds necessary to enable effective strategic and centralized management of the CP and enable efficient operations of portfolio capability components.

- Processes, engagement points, and methodologies for obtaining CP manager concurrence and for appealing non-concurrence decisions.

- Approach for resolution of disagreements.

- Internal and external relationships. (Required)

- Schedule. (Required)

- Process for annual budget development. (Required)

- Annual cost for operations and sustainment of the CP. (Required)

- Funding model(s). (Required)

- Approach for securing the appropriate level of funding. (Required)

- Customer charging methodologies. (Required)

- Sourcing strategy and approach for making sourcing decisions. (Required)

- Performance measurement. (Required)

- Approach and timeframe for developing the CP Strategic Development Plan. (Required)

- Plans for data management and risk management. (Required)

- Planned reviews. (Required)

#### The CPMP may take the form shown in the template provided in Appendix D or any other form as appropriate for the type, size, and complexity of the CP.

#### Center Directors and the JPL Lab Director who host CP capability components at their Centers and participating MDAAs shall concur or non-concur on the CPMP. A written explanation for a non-concurrence should be provided.

#### The sponsoring MDAA shall approve or disapprove the CPMP and provide rationale.

#### The CP manager shall revalidate or update the CPMP every five years. Updates may occur more frequently if there are significant changes as defined in the CPCA and as determined by the CP manager or sponsoring MDAA. The updated CPMP is reviewed and approved using the same process as the original.

#### The CP manager will ensure that the CPCA and CPMP are consistent in terms of content. If changes are required, the approval process for the applicable document(s) is followed.

### Conduct Reviews

#### Decisional Reviews

- Approval for Significant Changes to a Capability Portfolio

The MSC Chair shall conduct a decisional review when significant changes occur to a CP. Significant is defined in the CPCA and can include changes in the composition, management, or funding of the CP. The decisional review is held at the MSC.

- The CP manager, in coordination with the sponsoring Mission Directorate, will provide the materials needed to support the decisional review as described in Section 2.5.1. In addition to the materials described in Section 2.5.1, a description of the proposed change is provided. Changes may include changes to the management strategy, scope, total annual cost estimate, funding model(s), sourcing strategy, and the approach for making sourcing decisions for the CP. Examples of changes to scope include significant enhancements to existing portfolio capability components, addition of new capability components to the CP, and divestment of portfolio capability components.

- The CP manager will prepare a revised CPCA and CPMP to reflect the proposed change and will coordinate with affected stakeholders.

- As part of the decisional review, the MSC Chair will ensure that the change to the CP is aligned with the Agency’s vision and mission as defined in NPD 1001.0.

- The decision is documented in retrievable MSC documentation. The documentation should include the authorization to implement the change, any other decisions made, and any actions assigned. If no changes to the revised CPCA and CPMP are required following the decisional review, the approving authorities sign the revised documents. If changes are required, the revised CPCA and CPMP are updated, all signatures are obtained, and the documents are resubmitted to the approving authorities for final signature.

- Approval to Terminate a Capability Portfolio

If a need arises to terminate a CP, the MSC Chair shall conduct a decisional review to terminate the CP. The decisional review is held at the MSC.

- The CP manager, in coordination with the Mission Directorate, will provide the materials needed to support the decisional review as described in Section 2.5.1. In addition to the materials described in Section 2.5.1, these materials may include the rationale for Termination of the CP; the impact of Termination on the Agency or Mission Directorate; an estimate of the total cost of Termination; and a Termination strategy and close out plan, including reassignment of the CP’s assets and capability components.

- As part of the decisional review, the MSC Chair will ensure that the Termination of the CP is aligned with the Agency’s vision and mission as defined in NPD 1001.0.

- The Termination decision is documented in retrievable MSC documentation. The documentation should include the authorization to terminate the CP, any other decisions made, and any actions assigned.

#### Capability Portfolio Reviews

- The sponsoring MDAA and the CP manager shall lead or support the CP reviews identified in the CPCA and CPMP and other reviews required by this NPR.

- The CPMP includes the scope of planned CP reviews, the approach to conducting the reviews, the frequency and timeline for the reviews, the criteria (e.g., technical, cost, performance) that will be used in the reviews, and the review team(s) structure.

- The CP manager will select review team members for internal reviews and coordinate selection of review team members with the MDAA for stakeholder reviews and external reviews.

- The CP manager will ensure that planned reviews are accomplished in accordance with the CPMP and that results are adjudicated in a timely manner.

#### Other Reviews

The CP manager will support reviews of the CP as part of other Agency and Directorate reviews, such as the annual MSC CPM Annual Review and the Agency BPR where CPs report performance in the larger context of their sponsoring Mission Directorate.

## Capability Portfolio Termination

### If a need arises to terminate a CP, the CP manager, in consultation with stakeholders including Center Directors and the JPL Lab Director, the CIO, and participating MDAAs, will recommend Termination of the CP to the sponsoring MDAA. The sponsoring MDAA makes the recommendation to terminate the CP to the MSC Chair.

### The CP manager shall conduct Termination activities when approved by the MSC Chair. These include the following:

- Developing a Termination strategy and plan.

- Dissolving the  CPM structure and closing out all activities associated with the strategic and central management of the CP.

- Strategically decoupling the CP’s capability components.

- Reassigning the CP’s capability components, enabling infrastructure, and any other CP assets to Center management in accordance with the Termination strategy.

### The CP manager will develop a final CP report documenting results of the portfolio, such as performance relative to goals, technologies developed, lessons learned, and recommendations from the Termination review. The final report is captured as part of the MSC retrievable records and is managed in accordance with retrievable records. (See NPR 1441.1.)

# Capability Portfolio Roles and Responsibilities

## Summary of Specific Roles and Responsibilities

The roles and responsibilities of senior management are defined in NPD 1000.0 and further outlined in NPD 1000.3. This section delineates the roles and responsibilities specific to carrying out the requirements of this NPR.

### The MSC Chair:

- Approves the CPCA.

- Evaluates the performance of CPs against defined goals and objectives through reports from the MSC, which is the CP governing council, through the CPM Annual Review, which the MSC Chair conducts, and through Agency-level reviews, such as BPRs.

- Serves as the Decision Authority for CP decisional reviews including:

- The transition from Establishment activities to Strategic Management activities.

- Significant changes in the composition, management, or funding of the CP.

- The transition from Strategic Management activities to Termination activities.

### The MSC:

- Initiates efforts to establish CPs.

- Assigns CPs to sponsoring Mission Directorates.

- Reviews CP performance and provides reports to the MSC Chair.

### The OSI Assistant Administrator:

- Establishes Agency-level boards and teams, as needed, to address Agency-level CPM policies, issues, and strategies.

- Maintains the official list of CPs including a description of the CP and its scope and the capability domain, the capability components in the portfolio and their locations, and the name of the CP manager. The list of CPs can be found under the “Other Policy Documents” tab in the NASA Online Directive Information System (NODIS) on the OSI menu at https://nodis3.gsfc.nasa.gov/OSI_rep/OSI_list.cfm.

### Sponsoring MDAAs:

- Provide each CP manager, in writing, with the goals and objectives, capability domain and preliminary scope, and constraints of the relevant CP as part of the Establishment activities.

- Select a CP manager for each CP sponsored by their Mission Directorate.

- Establish a management and governance structure for each CP sponsored by their Mission Directorate.

- In coordination with the CP manager, establish and annually update a five-year CP budget commensurate with CP goals and objectives, CP operational norms, and funding responsibilities (one or more funding models) for each CP sponsored by their Mission Directorate.

- Develop the CPCA and recommend approval to the MSC Chair.

- Provide MDAA resources for the strategic and centralized management of each CP sponsored by their Mission Directorate and its components as defined in the CPCA and CPMP and ensure that resources are sized to meet the established goals and objectives.

- Support development of and approve the CPMP.

- Ensure sponsored CP capabilities are:

- Available to deliver products and services to the Agency in support of programs and projects.

- Consistent with NPD 1001.0.

- Functioning within established budget, schedule, and cost constraints.

- Conduct and/or support required CP reviews and report the CP status periodically to the MSC and Agency-level management.

- Determine the need for Termination of the CP upon consultation with the CP manager and other stakeholders and make recommendations to the MSC Chair.

- Serve as the selecting official for advisory boards.

### Both participating and sponsoring MDAAs:

- Collaborate with the CP manager to identify specific capability components (in-house or external) for products and services to meet Mission Directorate needs and requirements.

- Identify and inform the CP manager of requirements for new capability or enhanced capability that is needed to resolve identified capability gaps.

- Obtain concurrence from the CP manager on investments, divestments, acquisition strategies, procurements, agreements, and changes to a portfolio capability component in accordance with Section 3.2.1.10.

- Obtain and document CP leadership’s evaluation of and recommendations for proposals to be provided to Agency leadership that involve changes to the capability domain and fall within thresholds defined in the CPMP in accordance with Section 3.2.1.10.

- Concur or non-concur on a recommendation to terminate the CP. A written explanation for a non-concurrence should be provided.

- Participating MDAAs concur or non-concur on the CPCA and the CPMP for CP(s). A written explanation for a non-concurrence should be provided. (See Section 4.1.4 for the role of the sponsoring MDAA.)

- Assign a Mission Directorate CP POC for the CP.

- Assign representatives to Agency-level boards and teams as requested to address CPM policies, issues, and strategies.

- Support CP assessments and analyses as specified in the CPMP. Examples include providing information to support development of assessments and analyses, such as demand baseline requirements, annual demand forecast analyses, and the CP Strategic Development Plan.

- Support reviews required by this NPR.

- Provide Mission Directorate funding in accordance with the funding model(s) defined, documented, and agreed upon in the CPCA and CPMP.

- Coordinate with the CP manager and other key stakeholders to establish a consensus on cost elements that will meet the needs of the CP in developing the TCO for the portfolio and its components.

### The NASA Chief Engineer, MDAAs, and other entities that have responsibility for NASA capabilities as part of Capability Leadership:

- Appoint requested representatives to boards and teams to address CPM policies, issues, and strategies.

- Assign representatives to CP reviews and other reviews as required by this NPR.

- Provide technical support to the CP manager during the Establishment, Strategic Management, and Termination activities of CPs.

- Provide analysis and information to the CP manager on technical capability advancements or changes that might affect the CP.

- Coordinate with the CP manager on evaluations, analyses, prioritization, and identification of needed changes to the CP.

### The NASA Chief Financial Officer:

Supports CP managers in establishing TCO for the CP and its capability components.

### The NASA Chief Information Officer:

- Is a signature authority to the CPCA and CPMP for those CPs that are determined by the MSC to be inherently information technology.

- As the ITC Chair and Decision Authority, reviews and approves CP investments and divestments in information technology capabilities that are governed under NPD 2800.1 and NPD 2810.1.

- Appoints representatives to Agency-level boards and teams to address CPM policies, issues, and strategies.

- Appoints OCIO CP POCs for CPs that are determined by the MSC to be inherently information technology.

- Supports CP assessments and analyses as specified in the CPMP for CPs that are determined by the MSC to be inherently information technology.

### Center Directors and the JPL Lab Director:

- Manage, operate, and maintain the Center’s portfolio capability components and enabling infrastructure consistent with strategic guidance (included in approved CPCAs and CPMPs) that may include the funding level agreed upon by the CP manager for delivery of products and services to customers and approaches for adjusting the CORLs of portfolio capability components and their LoS.

- Provide Center resources in accordance with the funding model(s) defined, documented, and agreed upon in the CPCA and CPMP.

- Evaluate all work related to CPs that operate at the Center and provide the Center evaluation and assessment findings and recommendations to the CP manager in support of CP manager, MSC, and MSC Chair reviews of the CP.

- Coordinate with the CP manager and other key stakeholders to establish a consensus on cost elements that will meet the needs of the CP in developing the TCO for the portfolio and its components.

- Coordinate with the CP manager and other key stakeholders to establish agreement on cost estimating processes and guidelines and charging methodologies that will meet the needs of the CP.

- Develop cost estimates for planned delivery of products and services in accordance with the processes and guidelines defined in the CPMP. Guidelines may also be detailed in the baseline plan for the CP.

- Support CP managers in establishing the metrics necessary for strategic insight and management of the portfolio capability components at the Center as defined in the CPCA and CPMP.

- Manage and implement investment projects at the Center that are intended to improve existing portfolio capability components or add new capability components to a CP. Oversee and manage projects and tasks assigned to the Center that affect the CP, improve portfolio capability components, develop new capability components for CPs, and divest of portfolio capability components.

- Provide Center-level reports, assessments, and data for portfolio capability components that reside at the Center to support CP assessments and analyses as specified in the CPMP (e.g., demand baseline requirements, annual demand forecast analyses, and CP Strategic Development Plans).

- Support CP managers in defining operational norms between the CP manager, program and project managers (as appropriate), and Centers and in establishing any thresholds necessary to enable efficient operations of portfolio capability components at the Center. (Operational norms and thresholds are documented in the CPCA and CPMP.)

- Support CP managers in establishing key processes for strategically and centrally managing the CP(s) that include components at the Center.

- Appoint Center CP POCs for the CP(s) that include components at the Center.

- Appoint Center representatives to Agency-level boards and teams to address CPM policies, issues, and strategies.

- Assign Center representatives to CP reviews and other reviews as required (when the reviewer is not the Center CP POC).

- Concur or non-concur on the CPCA and the CPMP for CP(s) that include components at the Center. A written explanation for a non-concurrence should be provided.

- Concur or non-concur on a recommendation to terminate the CP. A written explanation for a non-concurrence should be provided.

- Seek customers for the Center’s portfolio capability components. Negotiate proposals with customers for products and services delivered by the Center’s portfolio capability components.

- Obtain concurrence from the CP manager on investments, divestments, acquisition strategies, procurements, agreements, and changes to a portfolio capability component in accordance with Section 3.2.1.11.

- Obtain concurrence from CP managers on the termination of plans for investments, divestments, and improvements that previously received CP manager concurrence in accordance with Section 3.2.1.11.c.

- Obtain and document the CP manager’s evaluation of proposals to be provided to Agency leadership that involve changes to the capability domain and fall within thresholds defined in the CPMP in accordance with Section 3.2.1.11.

- Obtain approval for alternate uses of portfolio capability components in accordance with Section 3.2.1.11.

### Program and project managers:

- Support CP assessments and analyses as specified in the CPMP. Examples include providing information to support development of assessments and analyses, such as demand baseline requirements, capability investments and divestments, and annual demand forecast analyses.

- Support CP managers in defining operational norms between the CP manager, program and project managers (as appropriate), and Centers and in establishing the thresholds necessary to enable efficient operations of portfolio capability components at the Center. (Operational norms and thresholds are documented in the CPCA and CPMP.)

- Obtain concurrence from the CP manager on investments, divestments, acquisition strategies, procurements, agreements, and changes to a portfolio capability component in accordance with 3.2.1.12.

- Obtain concurrence from CP managers on the termination of plans for investments, divestments, and improvements that previously received CP manager concurrence in accordance with Section 3.1.2.12.d.

- Obtain and document the CP manager’s evaluation of proposals to be provided to Agency leadership that involve changes to the capability domain and fall within thresholds defined in the CPMP in accordance with Section 3.2.1.12.

- Provide program and project resources in accordance with the defined customer charging methodologies defined, documented, and agreed upon in the CPCA and CPMP.

### CP managers:

- Establish processes and conduct Establishment, Strategic Management, and Termination activities for the CP.

- Develop and implement the sourcing strategy and approach for making sourcing decisions for assigning customer requirements (NASA and external) to capability components.

- Support the development of the CPCA, develop the CPMP, and prepare required updates to both documents.

- Determine the metrics necessary for strategic insight and management of the portfolio capability components.

- Establish a consensus with Center Directors and the JPL Lab Director and other key stakeholders on cost elements that will meet the needs of the CP in developing the TCO for the portfolio and its components.

- Determine the TCO for the CP and its capability components in accordance with the CPMP.

- Coordinate formulation of the budget with Center Directors and the JPL Lab Director, MDAAs, the CIO, and other key stakeholders to establish the CP funding process.

- Coordinate with customers and other stakeholders to identify sources of demand, demand characteristics (such as demand confidence, constraints, and purposes of need), capability gaps, and strategic requirements to inform both CP strategy and operational plans.

- Collaboratively define the operational norms between the CP manager and Centers and programs and projects to enable efficiency and effectiveness.

- Establish the thresholds necessary to enable effective strategic and centralized management of the portfolio (CP level) and enable efficient operations of portfolio capability components (Center level).

- Define the processes for obtaining concurrence and the processes for appealing non-concurrence decisions by the CP manager.

- Define the approach for resolution of disagreements.

- Establish charging methodologies for products and services.

- Define the approach for adjusting the CORLs of portfolio capability components and their LoS based on targeted Agency capacity and demand.

- Determine the need for and strategically manage investments, divestments, and the operational readiness of portfolio capability components in accordance with the CPMP.

- Identify, prioritize, select, and allocate the resources controlled by the CP manager.

- Conduct oversight of financial resources as defined in the CPMP.

- Recommend significant changes to the CP.

- Identify and resolve capability gaps for the portfolio based on future Agency requirements.

- Initiate, recommend an implementing organization for, and strategically and centrally manage projects and tasks associated with significant changes to and investments in the CP including establishing requirements, prioritizing work, and establishing funding. Provide strategic and centralized oversight for technical, cost, and schedule performance.

- Concur or non-concur on:

- Investments, divestments, acquisition strategies, procurements, agreements, and changes to a portfolio capability component in accordance with Section 3.2.1.8.

- The termination of plans for investments, divestments, and improvements that previously received CP manager concurrence in accordance with Section 3.2.1.8.

- Evaluate and make recommendations on proposals to be provided to Agency leadership that involve changes to the capability domain and fall within thresholds defined in the CPMP in accordance with Section 3.2.1.8.

- Approve or disapprove alternate uses of portfolio capability components in accordance with Section 3.2.1.8.

- Support and attend decisional reviews and lead or support CP reviews and other reviews required by this NPR.

- In consultation with stakeholders, including Center Directors and the JPL Lab Director, the CIO, and participating MDAAs, recommend Termination of the CP to the sponsoring MDAA.

# Dissenting Opinions and Tailoring Requirements

## 5.1	 Process for Handling Dissenting Opinions

### MDAAs, the OSI Assistant Administrator, and CP managers shall ensure Dissenting Opinions are elevated through the Dissenting Opinion process described in this section in accordance with the following principles:

- All participants within a CP will have full and open discussions with all facts made available to understand and assess issues.

- Diverse views are fostered and respected in an environment of integrity and trust with no suppression or retribution.

### Unresolved issues of any nature within a CP should be quickly elevated to achieve resolution at the appropriate level. In the teaming environment in which the CP operates, CP participants often have to determine where they stand on a decision. In assessing a decision or action, a CP participant has three choices: agree, disagree but be willing to fully support the decision, or disagree and raise a Dissenting Opinion. At the discretion of the dissenting person(s), a decision may be appealed to the next higher level of management for resolution.

### When time permits, the disagreeing parties jointly document the issue, including agreed-upon facts, discussion of the differing positions with rationale and impacts and the parties’ recommendations. The joint documentation is approved by the representative of each view, concurred with by affected parties, and provided to the next-higher level of management with notification to the second-higher level of management. In cases of urgency, the disagreeing parties may jointly present the information stated above orally with all affected organizations represented, advance notification to the second-higher level of management, and documentation follow up.

### Management’s decision/action on the dissent memorandum (or oral presentation) is documented and provided to the dissenter and to the notified managers and becomes part of retrievable MSC documentation. If the dissenter is not satisfied with the process or outcome, the dissenter may appeal to the next-higher level of management. The dissenter has the right to take the issue upward in the organization, even to the NASA Administrator if necessary.

## Tailoring Requirements

### NPR 1400.1 provides a process for tailoring requirements. The requirements in this NPR are minimized to allow flexibility for different CPs. However, if the need arises to tailor a requirement, a waiver is required from the requirements holder, OSI.

### The person requesting a waiver from a requirement of this NPR shall:

- Document the request including the rationale, a risk evaluation, and reference to all materials that provide the justification for acceptance.

- Obtain concurrence from the CP manager and the sponsoring MDAA, and the CIO (if the CP is inherently information technology or if the waiver is for requirements covered in Section 3.2.1.13).

- Submit the request to the OSI Assistant Administrator for approval and distribution in accordance with Table 5-1.

### Appendix E provides a template for a waiver request.

### The concurring and approving authorities shown in Table 5-1 shall adjudicate waivers from the requirements of this NPR.

Table 5-1 Waiver Approval for Capability Portfolios

| CP Manager | Concurs |
| --- | --- |
| Sponsoring MDAA | Concurs |
| CIO | Concurs* |
| OSI Assistant Administrator | Approves |
| Participating MDAAs | Concurs** |
| Center Directors and the JPL Lab Director | Concurs** |
| NASA Chief Engineer | Informed |

* The CIO concurs if the MSC has determined that the CP is inherently information technology or if the waiver is for requirements covered in Section 3.2.1.13.

** If the CP Manager and the OSI AA determine that the party is affected by the waiver.

Appendix A. Definition of Terms

Acquisition. Obtaining or advancing the development of the systems, research, services, construction, and supplies needed to fulfill the Agency’s mission and other activities that advance the Agency’s statutory objectives. As used in this document, the term encompasses all NASA acquisition authorities and approaches needed for that purpose.

Acquisition Strategy. The plan or approach for using NASA’s acquisition authorities to achieve the mission of a program or project. It includes the recommendations from make/buy and competed/directed analyses, proposed partnerships and contributions, proposed infrastructure use and needs, budget, and other applicable considerations.

Affordability. Fitting within the Agency resources allocated to manage, operate, sustain, and evolve a CP to meet current and projected customer requirements.

Agreement. The statement (oral or written) of an exchange of promises. Parties to a binding agreement can be held accountable for its proper execution, and a change to the agreement requires a mutual modification or amendment to the agreement or a new agreement.

Approval. Authorization by a required management official to proceed with a proposed course of action. Approvals are documented in retrievable records.

Asset. Any item of economic value owned by NASA including facilities and equipment and excluding personnel.

Capability. The ability of a system comprising workforce (i.e., Full-Time Equivalent (FTE)/Work-Year Equivalent (WYE)), competencies, assets, equipment, processes, and technologies to provide products and services to achieve objectives or meet requirements. (See also “Technical Capability.”)

Capability Component. An individual capability within a CP or the larger capability domain. It is a system comprising workforce (i.e., FTE/WYE), equipment, facilities, processes, resources, competencies, and technologies that delivers products and services; for example, a wind tunnel and the workforce that manages, operates, and maintains it or a complex dedicated to an end-to-end process.

Capability Domain. The in-house and external capabilities that characterize the broad realm of technical activities and associated products and services within which a CP falls. For example, the Aerosciences Evaluation and Test Capabilities (AETC) portfolio falls within the domain of wind tunnel and aero-propulsion testing. The capability domain and the associated boundaries of CP manager responsibilities are defined in the CPCA when the portfolio is established and are maintained as configuration-managed elements within the CPMP.

Capability Operational Readiness Levels. A tool for describing the operational readiness of portfolio capability components consistently across CPs. Operational readiness is defined in terms of ability and capacity to provide products and services to customers. This ability and capacity are based on the following:

- The asset/facility status of the capability component (the operational state of equipment and systems that comprise the capability component (e.g., active, inactive, mothballed) and current utilization (e.g., by a specific current program)).

- The personnel status of the capability component (the type of work the assigned personnel are able to perform and their expertise and skill levels (e.g., perform test and operations; perform preventive and corrective maintenance)).

There are seven capability operational readiness levels. (See Appendix F for additional information.)

Capability Portfolio. A specific collection of functionally similar site-specific capability components and enabling infrastructure strategically and centrally managed together to meet NASA’s strategic goals and objectives. For example, the Aerosciences Evaluation and Test Capabilities (AETC) portfolio includes selected NASA wind tunnels and aero-propulsion testing capability components. The CP is defined in the CPCA when the portfolio is established and is maintained as a configuration-managed element within the CPMP.

Capability Portfolio Advisory Board. A group of stakeholders chartered and chaired as described in the CPCA to address Agency-level CPM policies, issues, and strategies. The board may include Technical Fellows and others from relevant technical communities, such as OCIO. The board provides stakeholder and Agency guidance and input to the CP manager in the process of managing the CP. The board’s role is to facilitate Agency-wide communication and conflict resolution on issues surrounding demand and utilization and scalability (capacities and/or capabilities) for the CP.

Capability Portfolio Baseline Plan. An optional plan developed by the CP manager that details how the CP will be operated. The CP baseline plan is updated more frequently than the CPCA and CPMP and includes more detailed processes and guidelines for operations and interactions between the CP manager, Centers, and programs and projects. It may document any delegations from the CP manager to Centers, programs and projects related to sourcing decisions and committing the use of portfolio capability components through internal and external agreements. The CP baseline plan may also include cost estimating processes and guidelines. The CP baseline plan may be scoped to a single year of operation.

Capability Portfolio Commitment Agreement. An agreement between the MSC Chair and the sponsoring MDAA that is necessary for the CP to transition from Establishment activities to Strategic Management activities. The content of the initial CPCA reflects the maturity of the CP at the beginning of Strategic Management activities. Prior to approval of the CPCA, the sponsoring MDAA coordinates with the MSC Chair, the participating MDAAs, the Chief Information Officer (if the portfolio is inherently information technology), and the Center Directors and JPL Lab Director that have portfolio capability components that reside at their Centers to ensure their commitment to support the CP. (See Appendix C for detailed information on the content of the CPCA.)

Capability Portfolio Management. The centralized and strategic management of CPs to achieve NASA strategic goals and objectives.

Capability Portfolio Management Plan. An agreement between the sponsoring MDAA and the CP manager that details how the CP will be managed and is used by the governing council to determine if the CP is fulfilling its requirements. The CPMP is developed and approved within the timeframe specified in the CPCA. Prior to approval of the CPMP, the CP manager coordinates with the sponsoring MDAA, the participating MDAAs, the Chief Information Officer (if the portfolio is inherently information technology), and the Center Directors and the JPL Lab Director that have portfolio capability components that reside at the Centers to ensure their concurrence.

Capability Portfolio Manager. The person assigned to strategically and centrally manage a CP.

Capability Portfolio Representative. The person assigned to represent a particular organization on Agency-level boards and teams that address CPM policies, issues, and strategies.

Capability Portfolio Scope. The parameters that define the boundaries of a CP within a capability domain. For example, the scope of the Aerosciences Evaluation and Test Capabilities (AETC) portfolio includes large and strategically important wind tunnels and aero-propulsion testing capability components. The scope of a CP and the associated boundaries of CP manager responsibilities are defined in the CPCA when the portfolio is established and are maintained as configuration-managed elements within the CPMP.

Capability Portfolio Strategic Development Plan. A detailed description of the needed future state for the capability components within a CP and the processes for delivering products and services. The plan may be included in the CPMP or may be a separate document. (See Appendix D for detailed information on the content.) The plan:

- Defines the approach to evolving the set of portfolio capability components to better support current and future customers and requirements.

- Informs the development and prioritization of change to be implemented.

- Serves as a guide for assessing infrastructure improvements and associated investments including modernization, upgrades, and/or new construction.

- Addresses funding sources.

- Addresses the scope of projects that may be needed.

- Addresses strategic divestments and investments that need to be aligned with Center Master Plans and the Agency Master Plan.

Capacity. The planned availability of a capability component for customer utilization over a period of time. For example, the capacity of a wind tunnel is the available testing hours per year based on a provided level of resources and associated maintenance and other scheduled downtime.

Center Management Council. The council at a Center that performs oversight of portfolio capability components by evaluating all capability component work executed at that Center.

Centralized Management. A management, reporting, and communications approach led by a central authority to ensure tactical and strategic decisions are made at the appropriate levels and provide an integrated Agency perspective.

Component Facilities. Complexes that are geographically separated from the NASA Center or institution to which they are assigned but are still part of the Agency.

Classification and Decomposition Scheme. A method to represent the similarities, differences, and relationships between capability components within a CP. It may be represented in a hierarchical structure where similar capability components are grouped by salient attributes (e.g., Mach range for a wind tunnel; pounds thrust, fuels, and oxidizers for a propulsion test stand; temperature and pressure ranges for a thermal vacuum chamber). The classification and decomposition scheme may be used in analyses that include identification of redundancy and gaps within a CP. It may take the form of a spreadsheet, graph, or any other suitable format.

Concurrence. A documented agreement by a management official that a proposed course of action is acceptable.

Core Capability. The minimum workforce (FTE/WYE), competencies, assets, equipment, processes, and technologies below which NASA will assume unacceptable risk to current and future missions.

Customer. The intended user of the CP results. Typically, a customer is a Mission Directorate, a NASA program or project, or a Center. Customers may also be external entities.

Decision Authority. The individual authorized by the Agency to make important decisions on matters under their authority. For CPs, the MSC Chair is the Decision Authority.

Decisional Review. The event at which the MSC Chair determines the readiness of a CP to:

- Transition from Establishment activities to Strategic Management activities (including approval of the CPCA).

- Transition from Strategic Management activities to Termination activities.

- Make a significant change (“significant” is defined in the CPCA and approved by the MSC Chair) in the composition, management, or funding of the CP.

Demand Baseline. An aggregated collection of customer requirements for a CP. The demand baseline is confirmed annually by the customers (Mission Directorates, NASA programs and projects, Centers, and external entities) and updated as needed by the CP manager.

Directorate Program Management Council. The senior management group, chaired by an MDAA or designee, responsible for evaluating programs, projects, and CPs executed within that Mission Directorate and overseeing implementation according to Agency commitments, priorities, and policies.

Dissenting Opinion. A disagreement with a decision or action that is based on a sound rationale (not on unyielding opposition) that an individual judges is of sufficient importance that it warrants a specific review and decision by higher-level management, and the individual specifically requests that the dissent be recorded and resolved by the Dissenting Opinion process.

Divestment. The permanent removal of a capability component from the responsibility of a Federal entity through conveyance to another entity or destruction. Conveyance includes transfer of ownership or conversion to personal property. Destruction includes demolition, deconstruction, and natural or man-made events, such as fire, earthquake, flood, or explosion.

Enabling Infrastructure. Lesser facilities, structures, retention, supply, distribution, and control systems that are not directly part of a capability component or component facilities but are essential for its operations, such as gases and support fluids, propellants, high pressure water, steam, pumping stations, high voltage power systems, and equipment.

Establishment. The first of three sets of activities characterizing the lifespan of a CP. When leadership determines that it may be in NASA’s best interest to strategically and centrally manage a group of functionally similar capabilities in an integrated manner, it initiates the Establishment of a CP of capability components. Establishment activities include the following:

- Scoping and defining the portfolio.

- Designating its sponsoring Mission Directorate.

- Identifying the capability components of the portfolio.

- Developing a management strategy and approach.

- Selecting a CP manager.

- Preparing the CPCA.

A decisional review is held at the MSC to determine whether to formally establish a CP and transition to active strategic management status, i.e., to transition to Strategic Management activities.

Evaluation. The continual, self-, and independent (i.e., outside the advocacy chain of the CP) assessment of the performance of a CP and incorporation of the evaluation findings to ensure adequacy of planning and execution according to plan.

Funding Model. An approach for obtaining the needed level of funding to operate and sustain the CP and its components. Funding models are based on the estimated cost for the operations and sustainment of the CP at a defined capacity. Customer charging methodologies may or may not be included in the funding model. Funding models are defined in the CPCA and CPMP and reflect the Agency direction for the CP. (See the CPCA and CPMP for more details.)

Note: One or more funding models may be included in a CP; for example, different funding models for portfolio capability components or groups of components.

Gap Analysis. An assessment of the CP products and services needed by customers against the availability of those products and services to identify areas where availability may need to be modified.

Information Technology. Any equipment or interconnected system or subsystem of equipment that is used in the automatic acquisition, storage, manipulation, management, movement, control, display, switching, interchange, transmission, or reception of data or information by an executive agency. It also includes computers, ancillary equipment (including imaging peripherals, input, output, and storage devices necessary for security and surveillance), peripheral equipment designed to be controlled by the central processing unit of a computer, software, firmware and similar procedures, services (including support services), and related resources.

Information Technology Council. A decision-making body focused on information resources management that advises the NASA Chief Information Officer.

Investment. A resource and financial commitment made by the Agency, Mission Directorate, program, project, or Center.

Level of Service. The LoS establishes attributes related to the delivery of services by a CP, such as the scope of services, timeliness, times of operation, recovery from unplanned downtime, and service performance. The LoS may identify customer costs for different tiers of service performance and/or enhanced performance.

Metric. A measurement taken over a period of time that communicates vital information about the status or performance of a system, process, or activity.

Mission. A major activity required to accomplish an Agency goal or to effectively pursue a scientific, technological, or engineering opportunity directly related to an Agency goal.

Mission Support Council. The Agency’s senior decision-making body for the integrated Agency mission support portfolio. The council members are advisors to the MSC Chair. The MSC assesses and determines mission support requirements to enable the successful accomplishment of the Agency’s mission. The MSC is the governing council for CPs, initiates efforts to establish CPs, and assigns CPs to sponsoring Mission Directorates. It is the senior management group responsible for providing management oversight of a CP, its capability components, and related projects. The council has the responsibility of periodically evaluating the cost, schedule, risk, and performance of CPs under its purview. The evaluation focuses on whether the CP is meeting its commitments to the Agency and is following appropriate management processes.

Partner. An entity external to NASA with which NASA enters into an agreement. The entity may be a domestic non-governmental entity (i.e., academia, non-profits, commercial); a state, local, or Federal Government entity; or a foreign entity (i.e., foreign governments, foreign academia, and foreign commercial).

Participating Mission Directorate. A Mission Directorate that has a stakeholder interest in a CP.

Portfolio. A collection of projects, programs, capability components, sub-portfolios, and/or activities managed as a group to meet NASA’s strategic needs, goals, and objectives.

Procurement. Acquiring supplies or services (including construction) by contract with appropriated funds by and for the use of the Federal Government through purchase or lease, whether the supplies or services are already in existence or must be created, developed, demonstrated, and evaluated.

Program. A strategic investment by a Mission Directorate or Mission Support Office that has a defined architecture and/or technical approach, requirements, funding level, and a management structure that initiates and directs one or more projects. A program defines a strategic direction that the Agency has identified as needed to accomplish Agency goals and objectives.

Project. A specific investment having defined requirements, a life-cycle cost, a beginning, and an end. A project also has a management structure and may have interfaces to other projects, agencies, CPs, and international partners. A project yields new or revised products that directly address NASA’s strategic needs.

Resource. Budget, workforce, schedule, and other infrastructure elements that support NASA assets and can be used by individuals or organizations to facilitate effective functioning.

Risk. In the context of mission execution, the potential for performance shortfalls that may be realized in the future with respect to achieving explicitly established and stated performance requirements. The performance shortfalls may be related to any one or more of the following mission execution domains: (1) safety, (2) technical, (3) cost, and (4) schedule. (See NPR 8000.4.)

Risk Assessment. An evaluation of a risk item that determines: (1) what can go wrong, (2) how likely is it to occur, (3) what the consequences are, (4) what the uncertainties are that are associated with the likelihood and consequences, and (5) what the mitigation plans are.

Risk Management. An integrated framework for managing risk that includes Risk-Informed Decision Making (RIDM) and Continuous Risk Management (CRM). RIDM informs systems engineering decisions through better use of risk and uncertainty information in selecting alternatives and establishing baseline requirements. CRM manages risks over the course of strategic and centralized management of the CP to ensure that safety, technical, cost, and schedule requirements are met. (See NPR 8000.4.) These processes are applied at a level of rigor commensurate with the complexity, cost, and criticality of the CP.

Safety. Freedom from those conditions that can cause death, injury, occupational illness, damage to or loss of equipment or property, or damage to the environment.

Security. Protection of people, property, and information assets owned by NASA that covers physical assets, personnel, information technology, communications, and operations.

Significant Change. The types of change considered ‘significant’ for a CP are specified through thresholds, circumstances, criteria, and constraints in the CPCA. These may include the following:

- Changes in the composition (i.e., the scope including the addition of new portfolio capability components, important or major enhancements to existing portfolio capability components, or divestment of portfolio capability components).

- Management (strategy).

- Funding (total annual cost estimate and funding model(s)).

- Sourcing strategy of the CP.

- Approach for making sourcing decisions.

Sourcing Decisions. The assignment of customer requests to capability components.

Sourcing Strategy. A strategy for acquiring CP products and services through capabilities available in-house and through other agencies, vendors, partners, and academia. The sourcing strategy goal is to achieve an optimized portfolio that addresses Agency goals and objectives, supports the CP strategy, enables the CP’s strategic direction, and satisfies customer requirements.

Sponsoring Mission Directorate. The Mission Directorate assigned by the MSC to provide management and oversight of a CP.

Stakeholder. An individual or organization that is materially affected by the outcome or the deliverables of a CP but is outside the organization doing the work or making the decision; e.g., customers, beneficiaries, and organizations that work on or provide support to the CP.)

Strategic Management (function). A series of integrated efforts that enable the Agency to establish and execute strategy, make decisions, allocate resources, develop and implement plans, and measure performance of the CP.

Strategic Management (set of activities). The second of three sets of activities characterizing the lifespan of a CP. These activities include key CM management processes associated with both the strategic and centralized management aspects of CPM that repeat as long as the portfolio is active. They include the following:

- Maintaining a strategy.

- Supporting the budget process.

- Securing funding.

- Evaluating component capabilities and assets for need of maintenance, upgrade, or divestment.

- Analyzing the capability domain inside and outside of NASA.

- Understanding CP supply and demand.

- Assigning customer requirements to capability components that can deliver products and services in accordance with the approach for making sourcing decisions.

- Assessing the health of the CP and its component parts.

- Identifying and implementing new capabilities and improvements to the CP to meet future needs.

Sustained Tools of the Trade. Assets that:

- Are core to the business of the Center.

- Are in regular use by the Center.

- Are sustainably managed within the resources provided by the Center’s business base.

- May be commonly found in industry.

System. The combination of elements that function together to produce the capability required to meet a need. The elements include all hardware, software, equipment, facilities, personnel, processes, and procedures needed for this purpose.

Systems Engineering. A disciplined approach for the definition, implementation, integration, and operation of a system (product or service). The emphasis is on achieving stakeholder functional, physical, and operational performance requirements in the intended use environments over planned life within cost and schedule constraints. Systems engineering includes the engineering processes and technical management processes that consider the interface relationships across all elements of the system, other systems, or as a part of a larger system.

Tailoring. The process used to adjust or seek relief from a prescribed requirement to accommodate the needs of a specific task or activity. The tailoring process results in the generation of waivers.

Technical Capability. The equipment, facilities, infrastructure, property, support, and workforce required to accomplish a program or project. Technical capabilities are categorized into four types – discipline, system, research, and service.

Technical Fellow. A senior NASA technical expert supporting the Office of the Chief Engineer and the NASA Engineering and Safety Center. As an independent resource for the Agency and industry, a Technical Fellow:

- Resolves complex technical issues.

- Leads Agency-wide technical discipline teams and promotes discipline stewardship through workshops, conferences, and discipline enhancing activities.

- Fosters consistency of Agency-level standards and specifications and helps levy standards and specifications on major program/projects.

Termination. The third of three sets of activities characterizing the life span of a CP. When NASA leadership determines it is no longer in the Agency’s best interest to strategically and centrally manage a CP in an integrated manner, it initiates Termination of the portfolio. A Termination decision triggers activities including:

- Developing a Termination strategy and plan.

- Closing out all strategic and centralized management activities associated with the CP.

Threshold. A level (magnitude or intensity) specified in the CPCA or CPMP. Certain conditions occur with respect to a CP when thresholds are exceeded. Thresholds are used to enable the effective strategic and centralized management of the portfolio (CP level) and the efficient operation of portfolio capability components (Center level). For example, thresholds are established to identify:

- Significant changes that require decisional reviews.

- Assets to be included in a CP.

- Activities that require CP manager concurrence.

Total Cost of Ownership. A financial estimate intended to establish the full (direct and indirect) annual costs of operating and sustaining a CP and its capability components. The TCO is determined through processes established by the CP manager to support the need for differentiated understanding of costs in support of decision making to achieve CP efficiency and alignment. The TCO processes are documented in the CPMP.

Waiver. A written authorization granting relief from a requirement that results in more risk than is inherent in the original requirement. Waivers grant permanent or temporary relief after the original requirement is baselined for the specific product or process.

Appendix B. Acronyms

AO			NASA Announcement of Opportunity

BPR		Baseline Performance Review

CM&O	Center Management and Operations

CMC		Center Management Council
CORL		Capability Operational Readiness Level

CP			Capability Portfolio

CPCA		Capability Portfolio Commitment Agreement

CPM		NASA Capability Portfolio Management

CPMP		Capability Portfolio Management Plan

DPMC		Directorate Program Management Council

FTE		Full-Time Equivalent

ITC		Information Technology Council

LoS		Level of Service

MDAA 	Mission Directorate Associate Administrator

MSC		Mission Support Council

NASA		National Aeronautics and Space Administration
NOA		New Obligation Authority

NODIS	NASA Online Directives Information System

NPD 		NASA Policy Directive

NPR		NASA Procedural Requirements

OCE		Office of the Chief Engineer
OCHMO	Office of the Chief Health and Medical Officer

OCIO		Office of the Chief Information Officer

OSI		Office of Strategic Infrastructure
OSMA		Office of Safety and Mission Assurance

POC		Point of Contact

RPT		Rocket Propulsion Testing

SET		Space Environments Testing

TCO		Total Cost of Ownership

TRL		Technology Readiness Level

U.S.C.		United States Code

WYE 		Work-Year Equivalent

Appendix C. Capability Portfolio Commitment Agreement Template

C.1		CPCA Title Page

Capability Portfolio Commitment Agreement

(Provide a title for the CP and designate a short title or proposed acronym in parentheses if appropriate.)

It is the responsibility of each of the signing parties to notify the others in the event that a commitment cannot be met and to initiate the timely renegotiation of the terms of this agreement.

___________________________________			___________

Sponsoring Mission Directorate Associate Administrator 			     Date

___________________________________			___________

Participating MDAA(s)			     Date

___________________________________			___________

Center Director(s) and the JPL Lab Director			     Date

___________________________________			___________

Mission Support Council Chair			     Date

Figure C-1 Capability Portfolio Commitment Agreement Title Page

Note: The signature of the Chief Information Officer is added to the CPCA title page when the MSC determines that the CP is inherently information technology.

C.2	 CPCA Template

CAPABILITY PORTFOLIO COMMITMENT AGREEMENT

(CAPABILITY PORTFOLIO TITLE)

Required content is annotated by “Required.” Optional content is annotated by “Optional.” Optional content is recommended, if applicable. For information within the CPCA that changes frequently (e.g., schedules), the information within the document could simply be a pointer to where the authoritative current information resides.

1.0	GOALS AND OBJECTIVES

Required: Identify the relevant goals and objectives for the CP. Describe the CP’s relationship to the Agency’s vision and mission, as defined by NPD 1001.0, NASA Strategic Plan.

Required: Describe the CP’s relationship to the sponsoring Mission Directorate’s goals and objectives as documented in their strategic plan.

Required: Describe why the CP is required – describe customer (internal and external) needs and requirements that can be met through products and services provided by the CP.

Optional: Convey the public good of the CP to the taxpayer, stated in a way that can be understood by the average citizen.

2.0	DOMAIN, SCOPE, PRODUCTS, AND SERVICES DEFINITION

Required: Describe the capability domain, i.e., the in-house and external capabilities that characterize the broad realm of technical activities and associated products and services within which the CP falls.

Required: Describe the CP scope (in as much detail as possible), i.e., the parameters that define the boundaries of the CP within the capability domain.

Required: Define the CP (in as much detail as possible), including the capability components and enabling infrastructure to be strategically and centrally managed together in an integrated manner to meet NASA’s strategic goals and objectives.

Required: Provide a list or catalog of the capability components included in the CP including the facilities and enabling infrastructure at the NASA Centers.

Required: Identify capability components at NASA Centers that are within the capability domain of the CP but not included in the CP.

Required: Describe the planned products and services to be provided by the CP.

Optional: Describe the planned levels of service (LoS) within the CP necessary to deliver products and services to NASA’s programs and projects and external customers.

Optional: If applicable, provide a list or catalog of external sources – other agencies, industry, and academia.

Detailed lists and catalogs will be provided at https://nodis3.gsfc.nasa.gov/OSI_rep/OSI_list.cfm and may also be provided as separate documents or appendices as needed.

3.0	STRATEGY

Required: Describe the plan for how the CP will achieve its goals and objectives, including strategic themes and focus areas.

Required: Identify customers, stakeholders, and partners.

Required: Describe constraints on the CP and any opportunities.

Required: Describe the strategic direction for the evolution of the CP addressing strengths, weaknesses, capability gaps, investment priorities, risks, and risk mitigation.

Required: Identify the timeframe for completion of detailed planning and approval of the CPMP.

Required: Identify other documentation needed, such as a CP risk management plan. (Refer to NPR 8000.4.)

4.0	AUTHORITY, GOVERNANCE, AND MANAGEMENT

Required: Describe the NASA organizational structure, roles, and responsibilities for managing the CP and components from the MSC Chair and MSC to the sponsoring MDAA and DPMC to the Centers and CMCs involved. Include lines of authority and reporting for oversight of the CP.

Required: Identify the CP manager.

Required: Characterize the key CP parameters (e.g., cost, technical, products and services delivered, new capability components) that will require MSC Chair approval to change. Define the thresholds, criteria, and constraints that determine the need for a decisional review to approve CP actions and significant changes.

Optional: Define the operational norms (in as much detail as possible) between the CP manager and Centers, programs, and projects (as appropriate).

Optional: Define the thresholds and/or circumstances (in as much detail as possible) necessary to enable effective strategic and centralized management of the portfolio (CP level) and enable efficient operations of capability components (Center level).

(For detailed information on operational norms and thresholds, see Appendix D, Section 3.1.)

Required: Describe the approach for disagreement resolution.

5.0	PERFORMANCE

Required: Document how performance of the capability of the portfolio will be evaluated, including identification of performance metrics with goals and targets needed to achieve the CP objectives.

6.0	BUDGET DEVELOPMENT AND INTEGRATED FUNDING

Required: Identify the sponsoring MDAA resources for the strategic and centralized management of the CP and its components.

Required: Describe the estimated cost for the CP to operate.

Required: For the CP content, define annual budgetary estimates in support of a five-year budget, including specific estimates for operations, maintenance, and refurbishment and funding estimates for any planned strategic initiatives, renewals, or upgrades, including human resources and procurements.

Optional: Describe the budget contingency strategy.

Optional: Describe how the appropriate level of funding is secured to operate and sustain the CP and its components.

Required: Describe the funding model(s) specific to the CP in as much detail as possible and the cases of usage. (Funding models may vary from CP to CP and within a CP. For additional information on funding model(s), see Appendix D, Section 3.4.)

Required: Describe the funding elements necessary for the CP to achieve its strategic objectives that are budgeted outside of the CP budget, appearing instead as line items in the budgets of other areas of the Agency. Describe the CP’s need for reimbursable income and the estimated reimbursable funding from outside the Agency.

7.0	SOURCING STRATEGY AND SOURCING DECISIONS

Required: Describe the high-level sourcing strategy and the approach to making sourcing decisions in as much detail as possible. Details of the sourcing strategy and approach for making decisions are documented in the CPMP.

8.0	HIGH-RISK AREAS

Required: Identify the areas of highest risk for the CP (covering safety, technical, institutional, funding, cost, or schedule issues) in which failure may result in changes to the CP’s cost, schedule, or performance.

Optional: Identify, where possible, the specific risk drivers (e.g., unfunded mandates or an external facility or capability does not provide the agreed-upon level of access to NASA. Refer to NPR 8000.4.)

9.0	INTERNAL DEPENDENCIES AND AGREEMENTS

Required: Identify the NASA support from other Mission Directorates and Centers and the formal agreements necessary for the CP to meet its objectives.

10.0	EXTERNAL DEPENDENCIES AND AGREEMENTS

Required: Explain the partner support necessary to meet the CP’s objectives. Include a brief overview of relationships with each partner.

Optional: Identify the commitments being made by each partner and list the specific agreements to be entered into.

Optional: Clearly identify any unique considerations affecting the implementation of required NASA policies and processes that are necessitated by the external involvement.

11.0	REVIEWS

Required: Specify the type of CP reviews that are planned during Strategic Management to ensure the continued relevance (alignment with Agency vision and mission), performance, effectiveness, and affordability of the portfolio. Types of CP reviews include internal reviews conducted by the CP manager, sponsoring Mission Directorate reviews, advisory board reviews (if applicable), stakeholder reviews, and external reviews independently performed by outside organizations.

Optional: Provide the frequency and approximate timeframes for these reviews.

Required: Identify other reviews that the CP will support, such as the MSC CPM Annual Review and the Agency Baseline Performance Review (BPR).

Required: Identify any additional decisional reviews required by the MSC Chair during the Strategic Management set of activities.

12.0	WAIVERS

Required: Identify known waivers that will be sought for the CP. Provide rationale consistent with CP characteristics, such as scope, complexity, visibility, cost, safety, and acceptable risk.

13.0	CPCA ACTIVITIES LOG

Required: Provide and maintain a log of all CPCA activities, including revisions that reflect all changes and waivers to the original CPCA. This log includes the information shown in Table C-1 and may be supplemented with an attached addendum for each change that describes the change.

Required: The CPCA should be revalidated or updated every five years. Updates may occur more frequently if there are significant changes.

Table C-1 Sample Capability Portfolio Commitment Agreement Activities Log

| Date | Event | Change | Adden-dum | Term Review | Sponsoring MDAA Sign | Participating MDAA Sign | Center Director(s) and the JPL Lab Director Sign | MSC Chair Sign | CIO Sign when req’d |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| dd/mm/yy | Initial Signatures | None |  | No |  |  |  |  |  |
| dd/mm/yy | Revalidation | None | N/A | No |  |  |  |  |  |
| dd/mm/yy | Revalidation | None | N/A | No |  |  |  |  |  |
| dd/mm/yy | Approval of significant change | Addition of change N | Ref. #1 | No |  |  |  |  |  |

Appendix D. Capability Portfolio Management Plan Template

The MDAA may authorize use of an alternative format with compatible content.

D.1	   Capability Portfolio Management Plan Title Page

Capability Portfolio Management Plan

(Provide a title for the candidate CP and designate a short title or proposed acronym in parentheses, if appropriate.)

It is the responsibility of each of the signing parties to notify the others in the event that a commitment cannot be met and to initiate the timely renegotiation of the terms of this agreement.

___________________________________			___________

Capability Portfolio Manager			Date

___________________________________			___________

Participating MDAA(s)			Date

___________________________________			___________

Center Director(s) and the JPL Lab Director			Date

___________________________________			___________

Sponsoring Mission Directorate Associate Administrator			Date

Figure D-1 Capability Portfolio Management Plan Title Page

Note: The signature of the Chief Information Officer is added to the CPMP title page when the MSC determines that the CP is inherently information technology.

D.2	   Capability Portfolio Management Plan Template

CAPABILITY PORTFOLIO MANAGEMENT PLAN

(CAPABILITY PORTFOLIO TITLE)

Required content is annotated by “Required.” Optional content is annotated by “Optional.” Optional content is recommended, if applicable. For information within the CPMP that changes frequently (e.g., schedules), the information within the document could simply be a pointer to where the authoritative current information resides.

1.0	 CAPABILITY PORTFOLIO OVERVIEW

1.1	 Introduction

Optional: Briefly state the background of the CP and its current state including the results of establishing the portfolio, decisions, and documentation. If applicable, provide a brief description of intended future states and desired enhancements to address identified capability gaps.

1.2	 Goals and Objectives

Required: State the goals and specific objectives of the CP with clear traceability to the Agency’s vision and mission as defined by NPD 1001.0. Goals and objectives should include commitment to safety and mission success. Describe high-level objectives and how these objectives flow down from the CP to components.

1.3	 Customers, Beneficiaries, and Stakeholders Identification and Advocacy

Required: Identify the main customers, beneficiaries, and stakeholders of the CP and the process to be used to ensure customer and stakeholder advocacy.

1.4	 Domain, Scope, Products, and Services

Required: Describe the capability domain, i.e., the in-house and external capabilities that characterize the broad realm of technical activities and associated products and services within which the CP falls.

Required: Describe the CP scope, i.e., the parameters that define the boundaries of the CP within the capability domain.

Required: Define the CP, including the capability components and enabling infrastructure to be strategically and centrally managed together in an integrated manner to meet NASA’s strategic goals and objectives.

Required: Provide a list or catalog of the capability components included in the CP, including the facilities and enabling infrastructure at the NASA Centers.

Required: Describe the products and services to be provided by the CP.

Required: Describe the levels of service (LoS) within the CP necessary to deliver products and services to NASA’s programs and projects and external customers.

Required: Establish a description of the “core capability” of the portfolio, i.e., the minimum workforce (FTE/WYE), competencies, assets, equipment, processes, and technologies below which NASA will assume unacceptable risk to current and future missions.

Required: Identify and describe the insight needed into capability components that are within the capability domain of the CP but not included in the CP.

Detailed lists and catalogs will be provided at https://nodis3.gsfc.nasa.gov/OSI_rep/OSI_list.cfm and may also be provided as separate documents or appendices as needed.

Optional: If applicable, provide a list or catalog of external sources – other agencies, industry, and academia.

2.0	 AUTHORITY, GOVERNANCE, AND MANAGEMENT

Required: Identify the CP manager and the organization (Headquarters or Center) to which the CP manager reports.

Required: Describe the NASA organizational structure and detailed management roles and responsibilities for managing the CP from the MSC Chair and MSC to the sponsoring MDAA and DPMC to the Centers and CMCs involved including centralized management roles and responsibilities, lines of authority, and reporting.

Optional: Briefly describe the respective roles, responsibilities, and relationships between all parties involved in portfolio capability component operations and sustainment.

Required: Identify the responsibilities of each NASA Center as they relate to CP goals and objectives.

Optional: Illustrate the organization graphically.

3.0	 STRATEGIC MANAGEMENT

3.1	Activities

Required: Briefly describe the scheme for classification and decomposition of the CP.

Optional: Describe the way the CP will relate to other institutions within NASA as well as outside of NASA.

Optional: Establish a consensus with Center Directors and the JPL Lab Director and other key stakeholders on cost elements that will meet the needs of the CP in developing the TCO for the portfolio and its components.

Optional: Describe the process for estimating the TCO for the CP and its components.

Required: Describe the analytical process used to identify and prioritize investments and divestments to the CP to continuously align products and services with changing Agency needs and requirements and to support established objectives and targets for the CP.

Required: Describe the process by which projects initiated by the CP are approved and implemented.

Optional: Briefly discuss how policy and design and development efforts are coordinated to facilitate value-added consistency and standardization across capability components and investments in and divestments of systems, architectures, and technologies.

Optional: Briefly discuss how processes for providing products and services (e.g., customer service agreements, training procedures) are coordinated to facilitate value-added consistency and standardization.

Required: Define the operational norms between the CP manager and Centers, programs, and projects:

  - Establish the thresholds and/or circumstances necessary to enable effective strategic and centralized management of the portfolio (CP-level) and enable efficient operations of capability components (Center-level). Examples include thresholds and/or circumstances for concurrence from the CP manager for:

- Investments, improvements, and divestments of capability components.

- Internal and external implementation agreements for use of capability components.

- Obtaining products and services external to the CP.

- Proposed operational changes to a capability component.

- Significant changes to the CP baseline plan.

  - Describe the process and engagement points used to review and concur or non-concur. Examples include:

- Internal (e.g., between a Center and programs, projects, and other Centers) or external (e.g., Space Act, International) implementation agreements that commit the use of capability components.

- Proposed changes to the CP baseline plan.

- Investments, divestments, acquisition strategies, procurements, or agreements that seek to either build or develop new capabilities or improve or divest of existing capabilities that fall within the capability domain. Identify methodologies used to adapt concurrence processes to engagement points.

- Acquisition strategies, procurements, or agreements to obtain products and services from external capabilities that fall within the capability domain. Identify whether these concurrences are done at the individual acquisition strategy, procurement, or agreement level or at an integrated Center level and any applicable periodicity.

- Operational changes to a capability component within the CP.

- Termination of plans for investments, divestments, and improvements that previously received CP manager concurrence.

- Describe the appeal approach for Centers, programs, and projects for non-concurrence decisions by the CP manager.

- Describe the approach for disagreement resolution.

- Describe the approach for obtaining the CP manager’s evaluation of and recommendation for proposals to be provided to Agency leadership that involve changes to the capability domain.

- Identify whether a CP baseline plan will be used and if so, how it will be used.

- Describe any delegations of sourcing decisions to Center Directors and the JPL Lab Director, MDAAs, programs, or projects.

- Describe any assumption of program and project manager responsibilities by Center Directors and the JPL Lab Director.

- Describe CP scheduled meetings needed for centralized and strategic management (both informational and decisional).

- Describe the approach for adjusting the CORLs of portfolio capability components and their LoS.

- Describe the approach for approving alternate uses of portfolio capability components.

3.2	Schedule

Required: Provide a schedule of CP strategic activities and events and capability component utilization and CORL covering the next five years of the CP. The schedule may include applicable events, such as delivery dates for significant enhancements, major customer-scheduled milestones, scheduled reviews, and updates to the CPCA and CPMP.

The schedule may be provided as a separate document or appendix.

3.3	Alignment of Capacity with Demand

Required: Describe the current Agency and customer demand for the CP’s products and services.

Optional: When possible, provide a demand forecast for the next five years.

Required: Discuss how current and future Agency and customer demand for products and services is determined to ensure the CP’s ability and capacity (in-house and external) to meet that demand including any assumptions and data sources.

Optional: Describe how current available capacity (i.e., a combination of in-house and external) is matched to meet this demand.

Optional: Describe how significant discrepancies between capacity and demand will be resolved (e.g., changing the operational readiness of capability components or changing access to services from external sources).

3.4	Funding Model(s)

Required: Describe the process of developing the annual budget for the CP.

Required: Identify the TCO of the CP. Include all elements (such as operations, maintenance, and refurbishment) and funding estimates for any planned strategic initiatives, renewals, or upgrades; including workforce and procurements.

Required: Identify yearly New Obligation Authority (NOA) full-cost estimates for operations, facility construction, institutional support (maintenance), enhancements, technology, management and reserves in support of a five-year CP budget.

Required: Identify annual civil-service and contractor workforce levels that are funded with CP resources.

Required: Describe the funding model(s) specific to the CP and the cases of usage.

Required: Identify the sponsoring MDAA resources for the strategic and centralized management of the CP and its components. Describe CP funding model responsibilities levied on Centers, participating Mission Directorates, and other customers to support both fixed and variable costs (e.g., direct labor, consumables, materials, program-unique facility modernizations).

Required: Describe the approach for securing the appropriate level of funding to operate and sustain the CP and its components. Include a description of the different sources of funding and their approximate annual percentage (e.g., CM&O 15 percent, CP direct 55 percent, program direct 25 percent, reimbursable 5 percent).

Required: Include a description of the customer charging methodologies for products and services. This includes the principles and rules for customer charging that are used for detailed cost estimation. How different customers are charged is included within the principles and rules. The charging methodology for NASA program and project customers may differ from the charging methodology for various external customers. For example, the charging methodology for the Rocket Propulsion Testing (RPT) CP may include charging the customer for all resources required to bring a chemical propulsion test stand out of mothball status (CORL 6) to operational status (CORL 1 to 3), supplement the test stand staff for test activities, provide the consumables needed to support the test activities, and return the test stand to mothball status (CORL 6) once test activities are completed. The RPT CP manager is responsible for funding maintenance of all test stands in standby or mothball status (CORL 4, 5, and 6) as appropriate between tests.

Optional: Include a description of the cost estimating processes and guidelines used to develop detailed cost estimates for products and services.

3.5	Controls and Compliance

Optional: Describe the process by which the CP ensures compliance with NASA policies and directives, as well as other applicable requirements.

Required: Describe the process for controlling, tracking, and documenting changes.

Required: Characterize the key CP parameters (e.g., cost, technical, products and services delivered, new capability components) that will require sponsoring MDAA approval to change. Define the thresholds, criteria, and constraints that determine the need for sponsoring MDAA approval of CP actions and significant changes.

3.6	Relationships

3.6.1 Internal

Required: Identify the NASA support from other Mission Directorates, Offices (e.g., OCIO, OCE, Office of the Chief Health and Medical Officer (OCHMO), Office of Safety and Mission Assurance (OSMA)), and Centers.

Required: Identify formal agreements necessary for the CP to meet objectives.

Lists of agreements can be provided as separate documents or appendices as needed.

3.6.2 External

Required: Describe the external partner support necessary to meet CP objectives. Include a brief overview of relationships with each partner.

Required: Identify the commitments being made by each partner and list the specific agreements to be entered into.

Lists can be provided as separate documents or appendices as needed.

Optional: Clearly identify any unique considerations affecting implementation of required NASA policies and processes necessitated by the external involvement.

3.7	Sourcing Strategy and Sourcing Decisions

Required: Describe the sourcing strategy for acquiring CP products and services through capabilities available in-house and through other agencies, vendors, partners, and academia. Sourcing strategy considerations may include but are not limited to the following:

- Mission Directorate acquisition strategies.

- Mission risks.

- Center roles and responsibilities.

- Agency workforce priorities, including maintenance of internal competencies.

- Financial and schedule factors.

- In-house and external capacity.

- Maturity and availability of the capabilities of external sources.

- Specialized capability.

- Customer impacts.

- CP transformational objectives.

Optional: Describe the rationale for sustaining in-house capabilities, civil-service workforce, contractor workforce, and NASA facilities.

Optional: Describe how the appropriate balance between NASA sources and external sources is determined.

Optional: Provide a high-level evaluation of opportunities to leverage the expertise and capabilities of external sources.

Optional: Discuss how the CP periodically reevaluates the sourcing strategy to achieve an optimized portfolio including adjustments in response to changes in the products and services required by customers and changes in internal and external capabilities.

Required: Describe the approach for making sourcing decisions, i.e., assigning customer (NASA and external) requests to capability components. Sourcing decision considerations may include but are not limited to the following:

- The CP sourcing strategy.

- Alignment of capability component capabilities, capacity, availability, and constraints with customer requirements.

- Impact of using a non-local capability on customers and other stakeholders.

- Customer and other stakeholder.

- Need for product and service delivery at specific locations.

- Priorities for optimizing critical resources.

Required: Identify any delegation of responsibilities for sourcing decisions to Center Directors and the JPL Lab Director, MDAAs, program managers, or project managers.

3.8	Performance

Required: Describe how performance of the CP will be evaluated, including identification of performance metrics with goals and targets needed to achieve the CP objectives. Identify performance metrics in an objective, quantifiable, and measurable form.

3.9	Capability Portfolio Strategic Development Plan

Required: Describe the approach and timeframe for developing and maintaining a CP Strategic Development Plan. CP Strategic Development Plan content may include but is not limited to:

- The needed future state (combination of workforce (FTE/WYE), competencies, assets, equipment, processes, and technologies) for the capability components and the processes for delivering required products and services.

- How the CP evolves to achieve alternative methods and processes for delivery of products and services and alternative approaches to sourcing (i.e., balance of in-house and external).

- The alignment of the CP Strategic Development Plan with Agency and Center Master Plans.

- Principles and guidance for design and development of the CP and its components.

- How services, systems, architectures, technologies, processes, and metrics are consistent or standardized within the CP and among its components when it adds value.

- How future needs and requirements, capability gaps, technology trends, opportunities, threats, and changes to internal and external environment are identified, prioritized, and planned.

The CP Strategic Development Plan may be provided as a separate document or appendix.

3.10	Data Management

Required: Describe the approach to CP data management including what data will be captured, how the data will be collected, stored, described, organized, accessed, and archived; plans for data rights; plans for data services, and alignment with Agency information management and information technology security policies, standards, procedures, and waivers. Include documentation of changes.

Required: Describe the archival method for information used in support of decisional reviews, MSC decision packages, and MSC decisions related to the CP.

3.11	Risk Management

Required: Summarize the risk management process used for the CP, including appropriate actions to mitigate risk to the CP and actions to mitigate risks to customers as defined in NPR 8000.4.

4.0	 REVIEWS

Required: Specify the approach, criteria, and review team structure for planned CP reviews. Provide the frequency and approximate timeframes for these reviews.

Optional: Describe how the CP manager selects review team members for internal reviews and coordinates selection of review team members with the sponsoring MDAA for stakeholder reviews and external reviews.

Optional: Describe the approach to support other reviews, such as the MSC CPM Annual Review and the Agency Baseline Performance Review (BPR).

Required: Identify any additional decisional reviews required by the MSC Chair during the Strategic Management set of activities.

5.0	 RECORDS MANAGEMENT

Required: Describe how CP records will be managed as defined in NPR 1441.1.

6.0	 WAIVERS

Required: Identify known waivers that the CP has obtained or will obtain against NASA policies, directives, or applicable external requirements. Waivers will be archived consistent with Section 3.9, Data Management above.

7.0	 DISSENTING OPINIONS

Required: Briefly discuss the process for handling Dissenting Opinions.

8.0	 CPMP ACTIVITIES LOG

Required: Provide and maintain a log of all CPMP activities, including revisions that reflect all changes to the original CPMP. This log includes the information shown in Table D-1 and may be supplemented with an attached addendum for each change that describes the change. The CPMP should be revalidated or updated every five years. Updates may occur more frequently if there are significant changes.

Table D-1 Sample Capability Portfolio Management Plan Activities Log

| Date | Event | Change | Adden-dum | Decision Review | Sponsoring MDAA Sign | Participating MDAA(s) Sign | Center Director(s) and the JPL Lab Director Sign | CP Mgr. Sign | CIO Sign when req’d |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| dd/mm/yy | Initial signatures | None |  | No |  |  |  |  |  |
| dd/mm/yy | Revalidation | None | N/A | No |  |  |  |  |  |
| dd/mm/yy | Approval of significant change | Addition of change | Ref. #1 | Yes |  |  |  |  |  |

Appendix E. NPR 8600.x Waiver Template

| Name of Organization Requesting Waiver: | Date of Request: | Date Waiver is Needed: |
| --- | --- | --- |
| Name and Organization of Initiator: | Requirement to be Waived: |
| Specific Deliverable Affected: | Waiver To: ( Policy ( Procedure ( Requirement ( Other ( Additional information is attached |
| Original Requirement of Document to be Waived (list Appropriate Sections or Text): |
| Waiver Requested: |
| Reason/Justification (Attach additional information, if necessary): |
| Risk Assessment of the CP if Waiver is Approved: |
| Signatures | Signature | Date | Approve/Concur (Yes/No) |
| CP Manager (concurs) |  |  |  |
| Sponsoring MDAA (concurs) |  |  |  |
| Participating MDAAs (concur*) |  |  |  |
| Center Directors and the JPL Lab Director (concur*) |  |  |  |
| CIO (concurs*) |  |  |  |
| OSI Assistant Administrator (approves) |  |  |  |

*In accordance with Section 5.2.

Figure E-1 CPM Waiver Template

Appendix F. Capability Operational Readiness Level

F.1 	CORL OVERVIEW

F.1.1	Introduction

F.1.1.1 The CORL is a tool for describing the operational readiness of capability components consistently across CPs. Operational readiness is defined in terms of ability and capacity to provide products and services to customers. This ability and capacity are based on the Asset/Facility Status and Personnel Status of the capability component:

- The Asset/Facility Status is the operational state of equipment and systems that comprise the capability component (e.g., active, inactive, mothballed) and current utilization (e.g., by a specific current program). Facility status and utilization categories are described in NPR 8800.15.

- The Personnel Status is the type of work that assigned personnel are able to perform and their expertise and skill levels (e.g., perform test and operations; perform preventive and corrective maintenance).

F.1.1.2 There are seven levels of capability operational readiness. A summary of the seven CORLs, including the Asset/Facility Status and Personnel Status associated with each level, is provided in Table F-0. Detailed information for each CORL is provided in Tables F-1 through 
F-7.

F.1.2 	Potential Uses of CORL

Mission Directorates, CP managers, and Centers use the CORL to:

- Provide information on resources required to sustain a specific CORL for capability components.

- Provide information on resources required to transition a capability component from one CORL to another.

- Perform trades to determine the resources that could be saved by transitioning a capability component to a lower CORL.

- Effectively communicate to Agency management and stakeholders the implications of reduced budgets in terms of reduced CORLs for capability components.

F.1.3	CORL Summary

Table F-0 provides a summary of each CORL in terms of Facility Status and Personnel Status.

Table F-0 Capability Operational Readiness Level Summary

| # | Capability Operational Readiness Level | Asset/Facility Status | Personnel Status |
| --- | --- | --- | --- |
| 1 | Production Maximum or Maximum Capacity (1) | Active | Multiple Shift Operation – Able to Meet Unique Requirements or Staffing to Meet Maximum Production for Capability (2) |
| 2 | Intermediate/Extended Production or Intermediate/Extended Capacity (1) |  | Two-Shift Operation or Staffing to Meet Intermediate Production Level (3) |
| 3 | Production Minimum or Minimal Capacity (1) |  | Single-Shift Operation – Able to Meet Typical Requirements or Staffing to Meet Minimum Production Capability |
| 4 | Standby – Core Test and Maintenance Crew Only | Inactive - Standby | Core Test and Maintenance Personnel Only |
| 5 | Standby – Core Maintenance Crew Only |  | Core Maintenance Personnel Only |
| 6 | Dormant or Mothballed | Inactive - Mothballed | No Dedicated Personnel – Keeping Track of Core Personnel |
| 7 | Dispositioned or Divested | Inactive - Abandoned | No Dedicated Personnel |
|  |  | Dispositioned |  |

(1) CORL names are synonymous.

(2) May be less than three-shift operation.

(3) Approximate midpoint between CORL 1 and CORL 3.

F.2		CORL DETAILED DEFINITIONS

Tables F-1 through F-7 provide detailed information for CORLs 1 through 7, respectively.

Table F-1 Capability Operational Readiness Level 1

| # | Capability Operational Readiness Level | Asset/Facility Status | Personnel Status |
| --- | --- | --- | --- |
| 1 | Production Maximum or Maximum Capacity | Ability to (one or more may apply): - Prepare, test, and operate at maximum capacity. - Provide multiple shift operations (up to three). - Utilize multiple test positions simultaneously at different stages of preparation and testing. | Active | Utilization: - For specific current program, near-term program, or institutional requirement. - For reimbursable work as part of an agreement (e.g., Interagency, Space Act). Maintenance: - Fully maintained operational and safe; all preventive maintenance is performed. - Corrective maintenance is performed for safety. Storage: - Equipment not prepared for long-term storage. | Multiple Shift Operation – Able to Meet Unique Requirements or Staffing to Meet Maximum Production for Capability | Sufficient personnel (e.g., test crew) available to: - Prepare for and perform tests and operations. - Perform preventive and corrective maintenance. - Support up to three shifts and/or multiple test positions OR support maximum production for capability. Training and Certification: - Assigned personnel adequately trained and possess required certifications. |

Table F-2 Capability Operational Readiness Level 2

| # | Capability Operational Readiness Level | Asset/Facility Status | Personnel Status |
| --- | --- | --- | --- |
| 2 | Intermediate/Extended Production or Intermediate/Extended Capacity | Ability to (one or more may apply): - Prepare, test, and operate. - Provide multiple shift operations (up to two). - Utilize multiple test positions simultaneously at different stages of preparation and testing. | Active | Utilization: - For specific current program, near-term program, or institutional requirement. - For reimbursable work as part of an agreement (e.g., Interagency, Space Act). Maintenance: - Fully maintained operational and safe; all preventive maintenance is performed. - Corrective maintenance is performed for safety. Storage: - Equipment not prepared for long-term storage. | Two-Shift Operation or Staffing to Meet Intermediate Production Level (3) | Sufficient personnel available to: - Prepare and perform test and operations. - Perform preventive and corrective maintenance. - Support up to two shifts and/or multiple test positions OR support intermediate production level. Training and Certification: - Assigned personnel trained and possess required certifications. |

Table F-3 Capability Operational Readiness Level 3

| # | Capability Operational Readiness Level | Asset/Facility Status | Personnel Status |
| --- | --- | --- | --- |
| 3 | Production Minimum or Minimal Capacity | Ability to (one or more may apply): - Prepare, test, and operate using minimally required resources. - Provide one shift operation only with routine hardware/configuration. - Utilize only one test position when it is possible to simultaneously use several (possibly at different stages of preparation and testing). | Active | Utilization: - For a specific current program, near-term program, or institutional requirement. - For reimbursable work as part of an agreement (e.g., Interagency, Space Act). Maintenance: - Fully maintained operational and safe; all preventive maintenance is performed. - Corrective maintenance is performed for safety. Storage: - Equipment not prepared for long-term storage. | Single Shift Operation – Able to Meet Typical Requirements or Staffing to Meet Minimum Production Capability | Sufficient personnel available to: - Perform minimal test and operations. - Prepare for typical/routine tests or operations. - Perform preventive and corrective maintenance. - Ability to augment and train staff to achieve higher CORL. - Support one shift and/or one test position OR support minimum production for capability. Training and Certification: - Assigned personnel trained and possess required certifications. |

Table F-4 Capability Operational Readiness Level 4

| # | Capability Operational Readiness Level | Asset/Facility Status | Personnel Status |
| --- | --- | --- | --- |
| 4 | Standby – Core Test and Maintenance Crew Only | Personnel able to: - Perform preventive and corrective maintenance (personnel may be assigned to maintain multiple assets/facilities). - Augment and train additional personnel to achieve sufficient staff for operations and testing (CORL 1, 2, 3). Personnel unable to: - Prepare, test, and operate due to insufficient staff. - Personnel with “core” operational knowledge have primary duty to perform preventive and corrective maintenance. | Inactive -Standby | Utilization: - Temporarily not in use. - Will potentially be used to meet specific near-term or future program and/or institutional requirements. Maintenance: - Minimal preventive maintenance performed to maintain availability for test and/or operations. - Center or CP manager approved preventive maintenance to maintain essential systems in a state of availability for future use. - Minimal corrective maintenance performed for safety. Storage: - Equipment not prepared for long-term storage. | Core Test and Maintenance Personnel Only | Minimal “core” personnel available to: - Perform required approved preventive and corrective maintenance. - Maintain sufficient knowledge and experience to maintain and operate. - Augment and train staff to achieve CORL 1, 2, 3. - Maintain and utilize equipment to ensure continued operability and ability to return to “Active” status (CORL 1, 2, 3). |

Table F-5 Capability Operational Readiness Level 5

| # | Capability Operational Readiness Level | Asset/Facility Status | Personnel Status |
| --- | --- | --- | --- |
| 5 | Standby – Core Maintenance Crew Only | Personnel able to: - Perform preventive and corrective maintenance (personnel may be assigned to maintain multiple assets/facilities). Personnel unable to: - Prepare, test, and operate due to insufficient staff. - Train additional personnel for higher CORLs. - Staff may not possess right mix of “core” operational knowledge. | Inactive - Standby | Utilization: - Temporarily not in use. - Will potentially be used to meet specific near-term or future program and/or institutional requirements. Maintenance: - Minimal preventive maintenance performed to maintain availability for testing and/or operations. - Center or CP manager approved preventive maintenance measures to maintain essential systems in a state of availability for future use. - Minimal corrective maintenance performed for safety. Storage: - Equipment not prepared for long-term storage. | Core Maintenance Personnel Only | Minimal “core” personnel available to: - Perform approved preventive and corrective maintenance. - Maintain and utilize equipment to ensure continued operability and ability to return to “Active” status (CORL 1, 2, 3). |

Table F-6 Capability Operational Readiness Level 6

| # | Capability Operational Readiness Level | Asset/Facility Status | Personnel Status |
| --- | --- | --- | --- |
| 6 | Dormant or Mothballed | - Asset/facility deactivated, personnel reassigned. - No near-term program requirements. - Future requirements identified and/or capability retained to mitigate national and Agency-level risks. | Inactive - Mothballed | Utilization: - Deactivated. - No near-term program requirements. - Future requirements identified and/or the asset/facility maintained to mitigate national and Agency-level risks. Maintenance: - Center or CP manager approved preventive maintenance to prevent deterioration of essential systems or placed in protective storage. - Minimal corrective maintenance performed for safety. - Other corrective maintenance performed with Center approval. Storage: - Utility systems, collateral equipment shut down and prepared for long-term inactivity to prevent significant deterioration. - Selected systems (e.g., cathodic protection systems) kept in operation and inspected. - Interior environmental controls operating to prevent significant deterioration. - Exterior envelope inspected on planned basis, work performed as needed to maintain integrity of exterior shell. - In consultation with Center Environmental staff, hazardous materials identified and removed where appropriate. | No Dedicated Personnel – Keeping Track of Core Personnel | No Dedicated Personnel: - All personnel reassigned. - Personnel available only on part-time basis for preventive and corrective maintenance. - Center management tracks core personnel to reconstitute capability when and if needed. |

Table F-7 Capability Operational Readiness Level 7

| # | Capability Operational Readiness Level | Asset/Facility Status | Personnel Status |
| --- | --- | --- | --- |
| 7 | Disposi-tioned or Divested | - Deactivated, personnel are reassigned. - No near-term and future program requirements. | Inactive - Abandoned | Utilization: - Deactivated. - No plans for future reactivation. - No near-term and future program requirements. General: - Asset/facility systems and collateral equipment considered for excess and/or identified for use at other NASA locations. - Abandoned is an interim, temporary state used when it is not possible (e.g., resources not available, asset/facility integrated into a larger complex) or advantageous to “disposition” the asset/facility via the following - public benefit conveyance, Federal transfer, sale, lease termination, lease expiration, and demolition. Maintenance: - Asset/facility is in condition in which it has been “walked away from.” - Preventive and corrective maintenance ceased for all asset/facility systems, subsystems, equipment, and components (except for safety). Storage: - Utilities secured and disconnected at first service equipment location outside facility. - Asset/facility secured to prevent pilfering of economically salvageable materials. - In consultation with Center Environmental staff, hazardous materials identified and removed where appropriate. | No Dedicated Personnel | No Dedicated Personnel: - All personnel reassigned. - Personnel available only on task-order basis for preventive and corrective maintenance (for safety only). |
|  |  |  | Disposi- tioned |  |  |  |

Appendix G. References

G.1  Compliance

NASA Mission Directorates and Centers are required to comply with all applicable Agency directives, including but not limited to those listed in this appendix.

- The documents listed in this appendix are provided as a guide to help determine the requirements for CPM that are imposed outside this document.

- Relevant directives not cited in this document should be identified in Center processes and practices.

- Similarly, not all related references or other resources for CPM are identified.

G.2  NASA Policy Documents

- NPD 1000.5, Policy for NASA Acquisition.

- NPD 1050.1, Authority to Enter into Space Act Agreements.

- NPD 1200.1, NASA Internal Control.

- NPR 9090.1, Reimbursable Agreements.

- NPR 9420.1, Budget Formulation.

- NPR 9470.1, Budget Execution.

G.3  NASA Handbooks

a.	NASA/SP-2014-3705, NASA Space Flight Program and Project Management Handbook.

# Footnotes

If NASA leadership determines that it is no longer in NASA’s best interest to strategically and centrally manage a capability portfolio in an integrated manner, the portfolio may be terminated. (See Section 2.2.3.)

The MSC, whose responsibilities are documented in the MSC charter in NPD 1000.3, decided to appoint a team to issue directives to manage capability portfolios (Decision Memo MSC-2016-02-003a, dated June 2, 2017). Because the MSC has a vital role in managing these portfolios, it is necessary to describe MSC responsibilities in this NPR. These responsibilities will be captured in the next revision of the MSC charter, thereby providing traceability between the MSC charter and this NPR. NPD 1000.3 is scheduled to be revised.

The Mission Support Directorate is a Mission Directorate.

See NPR 8000.4 for more information.

CP managers collaborate with Center Directors and the JPL Lab Director, MDAAs, and in some cases program and project managers on responsibilities and may delegate specific responsibilities to them.

Responsibilities for sourcing decisions may be delegated by the CP manager to Center Directors and the JPL Lab Director, MDAAs, program managers, or project managers.

For example, for competed missions a statement may be inserted into applicable AOs covering the requirements of this policy.

Products and services from external capabilities that are procurement line items included in a product delivery are excluded, e.g., a spacecraft build and test delivery.

Center Directors and the JPL Lab Director may assume these responsibilities on behalf of program and project managers as agreed to in the CPMP.

Center Directors and the JPL Lab Director may assume these responsibilities on behalf of program and project managers as agreed to in the CPMP.

CP managers collaborate with Center Directors and the JPL Lab Director, MDAAs, and in some cases program and project managers on responsibilities and may delegate specific responsibilities to them.

Guidelines may also be detailed in the baseline plan for the capability portfolio.