| National Aeronautics and Space Administration Headquarters Washington, DC 20546-0001 |  |
| --- | --- |

NM 7120-40

NPR 7120.5C

SUPERSEDED BY NASA FAR Supplement (48 CFR 1834) 11/13/2006, NPR 7120.5D 03/06/2007, and active sections from NPR 7120.5C

March 6, 2006

Reply to Attn of:	Office of the Chief Engineer

TO:  		Officials-in-Charge of Headquarters Offices

Directors, NASA Centers

FROM:	Chief Engineer

SUBJECT: 	NASA Interim Directive to NPR 7120.5C, NASA Program and Project Management Processes and Requirements

The attached Interim Directive replaces NPR 7120.5C Section 3.4.3.2.a, which states the requirements for Earned Value Management; Section 3.1c, which describes the process for submitting deviations and waivers; and Appendix O, NPR 7120.5C Requirements Deviations and Waivers, which provides guidance for waiver/deviation requests and the Deviation/Waiver Form.

The major changes reflected in the Interim Directive include:

- Rescinding the requirement to apply a fully validated EVM system as defined by     EIA-748-A to all projects exceeding $50M in total project cost.  This Interim Directive requires EVM principles to be applied to flight and ground support projects exceeding $20M total project cost and requires EVM reports based on the EIA-748-A standard for all contracts exceeding $50M in initial or modified contract value.

- Requiring approval of the NASA Chief Engineer for waivers and deviations to requirements in NPR 7120.5C.

The Interim Directive is enclosed with this memorandum and will be submitted through the NASA Online Directives Information System (NODIS) official review process.  In parallel, the Office of the Chief Engineer is in the process of rescinding NPD 9501.3A, Earned Value Management, and NPR 9501.3, Earned Value Management Implementation on NASA Contracts.  This interim revision to NPR 7120.5C serves as the NASA policy for Earned Value Management until re-issuance of a revised Earned Value Management policy.

Please direct questions about the implementation of these requirements to the Mike Blythe in the Office of the Chief Engineer.  He can be reached at 202-358-3910.

Original signed by

Christopher J. Scolese

Enclosure

Responsible Office:  Office of the Chief Engineer

Subject:	NASA Interim Directive (NID):  NASA Procedural Requirement (NPR) 7120.5C, NASA Program and Project Management Processes and Requirements

The purpose of this NID is to issue interim requirement changes to NASA Procedural Requirement (NPR) 7120.5C, NASA Program and Project Management Processes and Requirements, in particular with respect to Earned Value Management (EVM) policy.

This NID shall be in effect for one year from the date of this memorandum, or until the release of an update to NPR 7120.5C, NASA Program and Project Management Processes and Requirements, whichever occurs first.  This NID applies to NASA Headquarters and NASA Centers, including Component Facilities.

The following describes the Interim Directive to NPR 7120.5C, NASA Program and Project Management Processes and Requirements:

- Section I replaces Chapter 3, Section 3.4.3.2.a.

- Section II replaces Chapter 3, Section 3.1c.

- Section III replaces Appendix O.  NPR 7120.5C Requirements Deviations and Waivers.

All other requirements established in NPR 7120.5C remain in effect.

Section I:

3.4.3.2.a  Execute the Project Control Plan.  The intent of this requirement is to maintain close configuration control of requirements, to assess the cost, technical and schedule status of the project relative to the NAR Baseline.  Therefore:

(1) 	EVM reports based on an EIA-748-A validated system shall be required on cost reimbursable contracts exceeding $50M in initial or modified contract value.

(2)	EVM principles as defined by EIA-748-A shall be applied to all flight systems and ground support projects (contractor and civil service) exceeding $20M total project cost.  However, the Mission Directorate Associate Administrator (MDAA) (or Mission Support Office Director (MSOD)) can require EVM principles be applied to any project or activity provided the necessary tools and resources are made available.

(3)	In implementing (1) and (2) above, the Project Manager shall ensure (for all applicable procurements) the appropriate provisions and clauses are included in solicitations and contracts.

(4) 	For projects requiring EVM, the Project Manager shall conduct and complete Integrated Baseline Reviews (IBRs) on projects to ensure the validity of the baseline.

(i)	The IBR shall be accomplished within six months after contract award or after approval of the Project Plan by the MDAA (or MSOD).

(ii)	The IBR shall be accomplished within two months after definitization of significant scope changes or after budget realignment.

(5)	Surveillance of contractor EVM systems is normally delegated to the Defense Contract Management Agency (DCMA) in accordance with the NASA/DCMA Memorandum of Understanding (MOU) for Earned Value Management System Acceptance/Surveillance and Earned Value Management Project Surveillance.  When such surveillance is to be delegated, the Project Manager shall, in coordination with the Contracting Officer, initiate the action for the Contracting Officer to issue a letter of delegation to the responsible DCMA activity.  The letter of delegation shall define the specific support, products, services, etc., to be provided by the DCMA.  (See FAR Part 42.2.)

(6)	Expenditures shall be accumulated according to the WBS established for the project and in as near-real time as possible.  Consistent with Continuous Cost-Risk Management (see reference L.2.a(1)), in addition to standard WBS-level performance measurement reporting, performance measurement of medium- and high-risk WBS elements identified during life-cycle cost estimation shall be provided to the Project Manager through specification in the Cost Performance Report (CPR) Data Requirements Description (DRD) and/or the Project Plan.

(7)	The full cost of civil service labor shall also be accumulated according to the WBS to permit later integration into full cost accounting and reporting.

(8)	Use of EVM is optional in contracts with research institutes and in grants of any type.  In such cases, when EVM is appropriate to the project but not to such project components, the Project Manager shall include in the Project Plan, Part 3, Project Control, the strategy for integrating cost and schedule aspects of those project components.

Section II.

3.1.c	Managers of projects identified in a Program Plan shall meet all requirements outlined in this chapter irrespective of the size of the project and the program of which it is an element.  Requests for deviations or waivers to NPR 7120.5C requirements shall be documented and submitted for approval to Project Manager, the Program Manager, the GPMC Chair and the NASA Chief Engineer.  The Project Manager should receive written authorization from the Office of Security and Program Protection for waiver of activities related to security.  Prior to the NAR, these requests shall be documented in the NPR 7120.5C compliance matrix attached to a single deviation or waiver to assure proper routing and control.  Deviations or waivers impacting formulation or requiring long lead-time shall be submitted individually early in formulation.  Following the NAR, deviations or waivers shall be submitted individually to the approving authority described above.  The compliance matrix, with approved deviations and waivers, shall be included as an appendix to the Project Plan.

Section III:

APPENDIX O.  NPR 7120.5C Requirements Deviations and Waivers.

This appendix provides information to guide requests for deviations or waivers to requirements provided in this document.

Requests for deviations or waivers to NPR 7120.5C requirements shall be documented and submitted for approval by the Project Manager, the Program Manager, the Governing PMC Chair, and the NASA Chief Engineer.

Prior to the NAR, these requests shall be documented in the NPR 7120.5 compliance matrix and attached to a single deviation or waiver to assure proper routing and control.  Deviations or waivers impacting formulation or requiring long lead time shall be submitted individually early in formulation.  Following the NAR, deviations or waivers must be submitted individually to the appropriate authority.

NPR 7120.5C Deviation/Waiver Form

| Name of Program or Project Requesting Deviation/Waiver: | Date of Request: | Date Deviation/Waiver is Needed: |
| --- | --- | --- |
| Name and Organization of Initiator : | Requirement to be Deviated/Waived: |
| Project Deliverable Affected: ( None ( Ground ( Flight ( Software ( Other | Deviation/Waiver To: ( Policy ( Procedure ( Requirement ( Other |
| Original Requirement of Document to be Deviated/Waived (list Appropriate Sections or Text) |
| Deviation/Waiver Requested: |
| Reason/Justification: |
| Risk Assessment of the Program and Project if Deviation/Waiver is Approved: |
| Approval Authority | Signature | Date | Approved (Yes/No) |
| Project Manager |  |  |  |
| Program Manager |  |  |  |
| GPMC Chair |  |  |  |
| NASA Chief Engineer |  |  |  |

# Officials-in-Charge of Headquarters Offices

Deputy Administrator/Ms. Dale

Associate Administrator/Mr. Geveden

Chief of Staff/Mr. Morrell

Deputy Chief of Staff and White House Liaison/Mr. Jezierski

Associate Administrator for Aeronautics Research Mission Directorate/Dr. Porter

Associate Administrator for Exploration Systems Mission Directorate/Dr. Horowitz

Associate Administrator for Institutions and Management/Mr. Sutton (Acting)

- Assistant Administrator for Diversity and Equal Opportunity/Dr. Hayden-Watkins

- Assistant Administrator for Human Capital Management/Ms. Dawsey

- Assistant Administrator for Infrastructure and Administration/Mr. Sutton

- Assistant Administrator for Procurement/Mr. Luedtke

- Assistant Administrator for Security and Program Protection/Mr. Saleeba

- Assistant Administrator for Small and Disadvantaged Business

Utilization/Mr. Balinskas (Acting)

- Chief Health and Medical Officer/Dr. Williams

- Executive Director, NSSC/Mr. Arbuthnot

Associate Administrator for Program Analysis and Evaluation/Dr. Pace

Associate Administrator for Science Mission Directorate/Dr. Cleave

Associate Administrator for Space Operations Mission Directorate/Mr. Gerstenmaier

Chief Engineer/Mr. Scolese

Chief Financial Officer/Ms. Sykes

Chief Information Officer/Ms. Dunnington

Chief Safety and Mission Assurance Officer/Mr. O’Connor

Chief of Strategic Communications/Mr. Davis

- Assistant Administrator for External Relations/Mr. O’Brien

- Assistant Administrator for Legislative Affairs/Mr. Chase

- Assistant Administrator for Public Affairs/Mr. Mould

- Chief Education Officer/Ms. Diaz (Acting)

General Counsel/Mr. Wholley

Inspector General/Mr. Cobb

# Directors, NASA Centers

Ames Research Center/Mr. Hubbard

Dryden Flight Research Center/Mr. Petersen

Glenn Research Center/Dr. Whitlow

Goddard Space Flight Center/Dr. Weiler

Jet Propulsion Laboratory/Dr. Elachi

Johnson Space Center/Mr. Coats

Kennedy Space Center/Mr. Kennedy

Langley Research Center/Ms. Roe

Marshall Space Flight Center/Mr. King

Stennis Space Center/Mr. Parsons

cc:

Executive Secretariat/Mr. Box

Senior Advisor to the Deputy Administrator/Mr. Hopkins

Office of the Administrator/Ms. Hutchinson

Assistant Associate Administrator/Ms. Johnson

Office of the Administrator/Ms. Mays

Senior Advisor to the Deputy Administrator/Mr. Ralsky

Special Assistant/Mr. Shank

Office of the Administrator/Ms. Soper

Office of the Deputy Administrator/Dr. Spyke

# Footnotes

These principles are listed here for clarity: (1) plan all work scope for the project to completion; (2) break down the project work scope into finite pieces that can be assigned to a responsible person or organization for control of technical, schedule, and cost objectives; (3) integrate project work scope, schedule, and cost objectives into a performance measurement baseline plan against which accomplishments may be measured and control changes to the baseline; (4) use actual costs incurred and recorded in accomplishing the work performed; (5) objectively assess accomplishments at the work performance level; (6) analyze significant variances from the plan, forecast impacts, and prepare an estimate at completion based on performance to date and work to be performed; and (7) incorporate Earned Value Management into the project’s decision-making and review processes.

EVM requirements are not levied on Basic and Applied Research and Advanced Technology Development projects, though project managers are encouraged to follow EVM principles on projects of significant size and scope.  Institutional projects that are developmental and not fixed price in nature (facility, IT investment, etc.) must comply with the requirements of this section.

The Compliance Matrix is provided as Appendix K.